## Sheet1
Project ID | Project Name | EBP Leader | Product Engineer | Project State | Phase 2 Gate Exit-DVR | Phase 3 Gate Exit-FPR | Phase 4 Gate Exit-CPA | 项目号 | 工作令号 | 项目名 | phase 2 score | phase 3 score | Phase 4 score
30033461 | 30033461-2026,AP,SVW,B-SUV-mirror,assy,260041,1M,Equipment | Wang Baowei_王保卫(uwanb363) | Chen Zhibin01_陈志斌(uchez368) | Phase 5 Production Delivery | 2026-05-30 | 2026-06-30 | 2026-07-31 | 30033461 | 260041 | SVW,B-SUV-mirror,assy | 1 | 1
30032706 | 30032706-2025,AP,SERES Motors,A15-mirror, assy, 260006, 15T,Equipment | Wang Baowei_王保卫(uwanb363) | Wang Wanfang_王万芳(uwanw356) | Phase 5 Production Delivery | 2026-05-10 | 2026-05-31 | 2026-06-30 | 30032706 | 260006 | SERES Motors,A15-mirror, assy | 1 | 1
30032370 | 30032370-2026,AP,SERES Motors,F3_Seat rail,Assy,250379,Equipment | Yang Yang28_杨阳(uyany430) | Huang Dinghui_黄定辉(uhuad002) | Phase 4 Manufacturing Development | 2026-03-31 | 2026-05-01 | 2026-08-31 | 30032370 | 250379 | SERES Motors,F3_Seat rail,Assy | 1 | 1
30033578 | 30033578-2026,AP,Tes,TBD_Click Rim, Lami, 260050, T,Equipment | Zou Chengcheng_邹成成(uzouc016) | Zhou Huasheng_周华盛(uzhoh176) | Phase 4 Manufacturing Development | 2026-05-12 | 2026-06-12 | 2026-08-31 | 30033578 | 260050 | Tes,TBD_Click Rim, Lami | 1 | 1
30033723 | 30033723-2026,AP,VW Group,VW426 PAB Chute Cell CI,260042,M,Equipment | Gong Shengchao_龚胜超(ugons034) | Wei Shaoguan_韦少官(uweis086) | Phase 5 Production Delivery | 2026-05-01 | 2026-06-01 | 2026-07-10 | 30033723 | 260042 | VW Group,VW426 PAB Chute Cell CI | 1 | 1
30034168 | 30034168-2026,AP,SVW,A-SUV-mirror,assembly,260008,15T,Equipment | Wang Baowei_王保卫(uwanb363) | Zhou Liwen_周理文(uzhol008) | Post Launch | 2026-05-18 | 2026-06-18 | 2026-07-18 | 30034168 | 260008 | SVW,A-SUV-mirror,assembly | 1 | 1
30034171 | 30034171-2026,AP,Jianghuai,JHC-sun visor,assy, 260074, NT,Equipment | Wang Baowei_王保卫(uwanb363) | Chen Zhibin01_陈志斌(uchez368) | Phase 4 Manufacturing Development | 2026-05-18 | 2026-06-18 | 2026-07-18 | 30034171 | 260074 | Jianghuai,JHC-sun visor,assy | 1 | 1
30034480 | 30034480-2028,AP,Toyota,780B,Spraying,260086,T,Equipment | Gong Shengchao_龚胜超(ugons034) | Kan Chengben_阚城奔(ukanc012) | Phase 2 Concept Definition | 2026-07-23 | 2026-07-24 | 2026-07-24 | 30034480 | 260086 | Toyota,780B,Spraying | 1 | 1
30034479 | 30034479-2027,AP,Toyota,780B,Spraying,260085,M,Equipment | Gong Shengchao_龚胜超(ugons034) | Chen Jie04_陈洁(uchej018) | Post Launch | 2026-06-26 | 2026-07-24 | 2026-07-24 | 30034479 | 260085 | Toyota,780B,Spraying | 1 | 1
30034478 | 30034478-2026,AP,Toyota,780B-DP, flaming,260080,T,Equipment | Gong Shengchao_龚胜超(ugons034) | Kan Chengben_阚城奔(ukanc012) | Phase 5 Production Delivery | 2026-06-30 | 2026-07-31 | 2026-08-12 | 30034478 | 260080 | Toyota,780B-DP, flaming | 1 | 1
30034477 | 30034477-2025,AP,Toyota,780B-DP,Flaming, 260079,M,Equipment | Gong Shengchao_龚胜超(ugons034) | Huang Linjian_黄琳健(uhual254) | Phase 4 Manufacturing Development | 2026-07-30 | 2026-08-13 | 2026-08-27 | 30034477 | 260079 | Toyota,780B-DP,Flaming | 1 | 1
30034166 | 30034166-2026,AP,SAIC-GM,C1UL-2,CNSL,Lamination,260073,T,Equipment | Shang Bing_尚兵(ushab007) | Fan Aiqiang01_樊爱强(ufana018) | Phase 4 Manufacturing Development | 2026-06-11 | 2026-06-28 | 2026-07-28 | 30034166 | 260073 | SAIC-GM,C1UL-2,CNSL,Lamination | 1 | 1
30034615 | 30034615-2026,AP,BYD,MR&ST-IP, Glue,260091, M,Equipment | Yuan Shuai_袁帅(uyuas003) | Chen Jie04_陈洁(uchej018) | Phase 4 Manufacturing Development | 2026-05-30 | 2026-06-30 | 2026-07-30 | 30034615 | 260091 | BYD,MR&ST-IP, Glue | 1 | 1
30035096 | 30035096-2026,AP,smartmi,F2N-light,welding260130,M,Equipment | Chen Jiarong_陈佳荣(uchej731) | Wei Shaoguan_韦少官(uweis086) | Phase 3 Design Feasibility | 2026-07-03 | 2026-08-03 | 2026-09-02 | 30035096 | 260130 | smartmi,F2N-light | 1 | 1
30034747 | 30034747-2026,AP,Huawei Anhui,X90-DP,260116,Glue spray,M,Equipment | Shang Bing_尚兵(ushab007) | Cheng Debao_程德宝(uched025) | Phase 4 Manufacturing Development | 2026-05-16 | 2026-05-31 | 2026-07-31 | 30034747 | 260116 | Huawei Anhui,X90-DP | 1 | 1
30034746 | 30034746-2026,AP,Huawei Anhui,X90-DP,260115,glue spray,M,Equipment | Shang Bing_尚兵(ushab007) | Cheng Debao_程德宝(uched025) | Phase 4 Manufacturing Development | 2026-05-23 | 2026-06-06 | 2026-07-18 | 30034746 | 260115 | Huawei Anhui,X90-DP | 1 | 1
30034624 | 30034624-2026,AP,BYD,Lamination,260102,M,Equipment | Shang Bing_尚兵(ushab007) | Huang Linjian_黄琳健(uhual254) | Phase 4 Manufacturing Development | 2026-05-16 | 2026-05-30 | 2026-07-31 | 30034624 | 260102 | BYD,Lamination | 1 | 1
30033409 | 30033409-2026,AP,Huawei Anhui,F05/F03 CNSL,Assembly,260037,M,Equipment | Meng Zibing_孟子冰(umenz002) | Feng Quanhua_冯全华(ufenq022) | Phase 4 Manufacturing Development | 2026-05-31 | 2026-06-30 | 2026-07-31 | 30033409 | 260037 | Huawei Anhui,F05/F03 CNSL,Assembly | 1 | 1
30033407 | 30033407-2026,AP,Huawei Anhui,F05/F03 CNSL,Assembly,260036,M,Equipment | Meng Zibing_孟子冰(umenz002) |  | Phase 5 Production Delivery | 2026-04-30 | 2026-05-31 | 2026-06-30 | 30033407 | 260036 | Huawei Anhui,F05/F03 CNSL,Assembly | 1 | 1
30033405 | 30033405-2026,AP,Huawei Anhui,F05 IP,Assembly,260038,M,Equipment | Meng Zibing_孟子冰(umenz002) |  | Phase 5 Production Delivery | 2026-04-30 | 2026-05-31 | 2026-06-30 | 30033405 | 260038 | Huawei Anhui,F05 IP,Assembly | 1 | 1
30033376 | 30033376-2026,AP,Huawei Anhui,F05&F03,Assembly,260031,T,Equipment | Meng Zibing_孟子冰(umenz002) |  | Phase 5 Production Delivery | 2026-04-30 | 2026-05-21 | 2026-06-30 | 30033376 | 260031 | Huawei Anhui,F05&F03,Assembly | 1 | 1
30033375 | 30033375-2026,AP,Huawei Anhui,F05&F03,Assembly,260032，T,Equipment | Meng Zibing_孟子冰(umenz002) |  | Phase 5 Production Delivery | 2026-04-30 | 2026-05-19 | 2026-06-30 | 30033375 | 260032 | Huawei Anhui,F05&F03,Assembly | 1 | 1
30033373 | 30033373-2026,AP,Huawei Anhui,F03F05,Assembly,260030,T,Equipment | Meng Zibing_孟子冰(umenz002) |  | Phase 5 Production Delivery | 2026-04-30 | 2026-05-19 | 2026-06-30 | 30033373 | 260030 | Huawei Anhui,F03F05,Assembly | 1 | 1
30035325 | 30035325-2026,AP,SERES Motors,遮阳板,1200压机,260145,1M,Equipment | Meng Zibing_孟子冰(umenz002) |  | Phase 5 Production Delivery | 2026-05-22 | 2026-06-02 | 2026-06-30 | 30035325 | 260145 | SERES Motors遮阳板1200压机 | 1 | 1
30035209 | 30035209-2026,AP,Jianghuai,C673-DP,Foam sticking,T,Equipment | Shang Bing_尚兵(ushab007) | Chen Zhibin01_陈志斌(uchez368) | Phase 4 Manufacturing Development | 2026-06-13 | 2026-06-30 | 2026-08-15 | 30035209 | 000000 | JianghuaiC673-DPFoam sticking | 1 | 1
30035208 | 30035208-2026,AP,Jianghuai,C673-DP,Foam Sticking,260140,M,Equipment | Shang Bing_尚兵(ushab007) | Chen Zhibin01_陈志斌(uchez368) | Phase 4 Manufacturing Development | 2026-06-13 | 2026-06-30 | 2026-07-31 | 30035208 | 260140 | JianghuaiC673-DPFoam Sticking | 1 | 1
30035205 | 30035205-2027,AP,SERES Motors,E68-DP,lamination,260138,2M,Equipment | Yuan Shuai_袁帅(uyuas003) | Huang Linjian_黄琳健(uhual254) | Phase 4 Manufacturing Development | 2026-06-30 | 2026-07-30 | 2026-08-28 | 30035205 | 260138 | SERES MotorsE68-DPlamination | 1 | 1
30035188 | 30035188-2026,AP,smartmi,KUNLUN-light,welding.260135.M,Equipment | Chen Jiarong_陈佳荣(uchej731) | Wei Shaoguan_韦少官(uweis086) | Phase 4 Manufacturing Development | 2026-07-04 | 2026-08-04 | 2026-09-03 | 30035188 | 260135 | smartmiKUNLUN-lightwelding.260135.M | 1 | 1
30034579 | 30034579-2026,AP,BYD,Glue,260095,M,Equipment | Shang Bing_尚兵(ushab007) | Chen Jie04_陈洁(uchej018) | Phase 4 Manufacturing Development | 2026-07-06 | 2026-08-06 | 2026-09-05 | 30034579 | 260095 | BYDGlue260095 | 1 | 1
30034578 | 30034578-2026,AP,BYD,Glue,260093,M,Equipment | Shang Bing_尚兵(ushab007) | Chen Jie04_陈洁(uchej018) | Phase 4 Manufacturing Development | 2026-07-04 | 2026-08-04 | 2026-09-03 | 30034578 | 260093 | BYDGlue260093 | 1 | 1
30034577 | 30034577-2026,AP,BYD,EHX,Glue,260088,M,Equipment | Shang Bing_尚兵(ushab007) | Chen Jie04_陈洁(uchej018) | Phase 4 Manufacturing Development | 2026-07-04 | 2026-08-04 | 2026-09-03 | 30034577 | 260088 | BYDEHXGlue | 1 | 1
30017341 | 30017341-2024,AP,BYD,SA5-IP,Lamination,220281,M,Equipment | Shang Bing_尚兵(ushab007) |  | Phase 4 Manufacturing Development | 2026-07-04 | 2026-08-04 | 2026-09-03 | 30017341 | 220281 | BYDSA5-IPLamination | 1 | 1
30035162 | 30035162-2026,AP,BJEV,X90,Lamination,260133,M,Equipment | Shang Bing_尚兵(ushab007) | Chen Jie04_陈洁(uchej018) | Phase 4 Manufacturing Development | 2026-06-26 | 2026-07-18 | 2026-07-31 | 30035162 | 260133 | BJEVX90Lamination | 1 | 1
30035161 | 30035161-2026,AP,BJEV,X90,Lamination,260132,M,Equipment | Shang Bing_尚兵(ushab007) | Chen Jie04_陈洁(uchej018) | Phase 2 Concept Definition | 2026-06-20 | 2026-06-30 | 2026-07-31 | 30035161 | 260132 | BJEVX90Lamination | 1 | 1
30035707 | 30035707-2026,AP,Brilliance-BMW,RGB 8PIN-light,assemble,260156,T,Equipment | Chen Jiarong_陈佳荣(uchej731) | Zhou Liwen_周理文(uzhol008) | Phase 4 Manufacturing Development | 2026-07-11 | 2026-07-18 | 2026-08-01 | 30035707 | 260156 | Brilliance-BMWRGB 8PIN-lightassemble | 1 | 1
30034299 | 30034299-2026,NA,Ford,P780-DP,Lamination,260077,M,Equipment | Wang Xiang02_王翔(uwanx029) | Huang Linjian_黄琳健(uhual254) | Phase 4 Manufacturing Development | 2026-03-13 | 2026-03-26 | 2026-08-31 | 30034299 | 260077 | P780 2050 单工位压机 | 1 | 1
30033911 | 30033911-2026,NA,Stellantis,WL-DP,laminnation,260060,T,Equipment | Wang Xiang02_王翔(uwanx029) | Jin Yulong01_金宇隆(ujiny132) | Phase 4 Manufacturing Development | 2026-07-10 | 2026-07-31 | 2026-08-21 | 30033911 | 260060 | StellantisWL-DPlaminnation | 1 | 1
30034479B/C/D | 30034479-2027,AP,Toyota,780B,Spraying,260085,M,Equipment | Gong Shengchao_龚胜超(ugons034) | Chen Jie04_陈洁(uchej018) | Phase 2 Concept Definition | 2026-06-26 | 2026-07-24 | 2026-07-24 | 30034479 | 260085 | Toyota,780B,Spraying | 1 | 1
30034473_ | 30034473-2026,AP,SERES Motors,F2N-light,260082,M,Equipment | Chen Jiarong_陈佳荣(uchej731) | Hao Xiuxia_郝秀霞(uhaox031) | Phase 5 Production Delivery | 2026-04-24 | 2026-04-30 | 2026-06-30 | 30034473 | 260082 | SERES Motors,F2N-light | 1 | 1
30033915 | 30033915-2026,NA,Stellantis,WL-DP,lamination,260063,T,Equipment | Wang Xiang02_王翔(uwanx029) | Huang Linjian_黄琳健(uhual254) | Phase 4 Manufacturing Development | 2026-03-31 | 2026-04-30 | 2026-07-31 | 30033915 | 260063 | StellantisWL-DPlamination | 1 | 1
30033914 | 30033914-2026,NA,Stellantis,WL-DP,lamination,260062,T,Equipment | Wang Xiang02_王翔(uwanx029) | Huang Linjian_黄琳健(uhual254) | Phase 4 Manufacturing Development | 2026-03-30 | 2026-04-30 | 2026-07-31 | 30033914 | 260062 | StellantisWL-DPlamination | 1 | 1
30033913 | 30033913-2026,NA,Stellantis,WL-DP,lamination,260061,T,Equipment | Wang Xiang02_王翔(uwanx029) | Jin Yulong01_金宇隆(ujiny132) | Phase 4 Manufacturing Development | 2026-03-26 | 2026-04-30 | 2026-07-30 | 30033913 | 260061 | StellantisWL-DPlamination | 1 | 1
30036187 | 30036187-2026,NA,Ford,P780-DP,Lamination,260182,M,Equipment | Wang Xiang02_王翔(uwanx029) | Huang Linjian_黄琳健(uhual254) | Phase 4 Manufacturing Development | 2026-06-30 | 2026-07-10 | 2026-08-31 | 30036187 | 260182 | FordP780-DPLamination | 1 | 1
30036186 | 30036186-2026,NA,Ford,P780,-DP,Lamination,260181,M,Equipment | Wang Xiang02_王翔(uwanx029) | Huang Linjian_黄琳健(uhual254) | Phase 4 Manufacturing Development | 2026-06-30 | 2026-07-10 | 2026-08-31 | 30036186 | 260181 | FordP780-DP | 1 | 1
30032099 | 30032099-2027,NA,Volkswagen,VW426-IP,Assembling,250365,M,Equipment | Wang Xiang02_王翔(uwanx029) | Liu Jinghua01_刘璟华(uliuj595) | Phase 5 Production Delivery | 2025-12-31 | 2026-01-31 | 2026-03-31 | 30032099 | 250365 | VolkswagenVW426-IPAssembling | 1 | 1