## Sheet1
Project ID | Project Name | EBP Leader | Product Engineer | Project State | PKR_S | PKR | P2 | P3 | P4 | 备注 | SSO_S | SSO_issue | Phase 2 Gate Exit-DVR | Phase 3 Gate Exit-FPR | Phase 4 Gate Exit-CPA | 工作令号
30030913-EBP | 30030913-2026,AP,Chery,E0V-Vent,EOL,250310,T,Equipment | 王翔 | 韦少官 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  | 无重大安全问题 发运前安全分93.1% | 2025-10-16 | 2025-10-31 | 2026-03-31 | 250310
30030865-EBP | 30030865-2027,AP,Audi FAW NEV,Au40x PA DP-Welding,250311,M,Equipment | 赵军 | 郝秀霞 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-12-07 | 2026-01-07 | 2026-02-06 | 250311
30030832-EBP | 30030832-2026,AP,smartmi,MS12-light,assemble，250302，T,Equipment | 陈佳荣 | 陈志斌 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  | 无重大安全问题 发运前安全分96.97% | 2025-11-22 | 2025-12-23 | 2026-01-22 | 250302
30030761-EBP | 30030761-2025,AP,SAIC-VW,VW416-IP,Automatin,250306,M,,Equipment | 夏阳 | 刘璟华 | Phase 1 Quotation |  |  | G | G | G |  |  | 无重大安全问题 发运前安全分93.5% | 2026-05-31 | 2026-06-30 | 2026-07-31 | 250306
30030728-EBP | 30030728-2026,AP,SERES Motors,F1L Sunvisor,Assy,250303,T,Equipment | 孟子冰 | 黄定辉 | Phase 5 Production Delivery | 2025-10-21 |  | R | R | R |  |  | 无重大安全问题 发运前安全分96.67% | 2025-10-31 | 2025-10-31 | 2026-01-15 | 250303
30030654-EBP | 30030654-2025,AP,smartmi,kunlun-light,assemble,250301,M,Equipment | 陈佳荣 | 冯全华 | Phase 4 Manufacturing Development | 2025-09-18 |  | R | R | R | 车间 |  | 无重大安全问题 发运前安全分82.88% | 2025-10-12 | 2025-11-09 | 2026-01-31 | 250301
30030630-EBP | 30030630-2026,AP,SVW,VW416-8,EOL,250296,T,Equipment | 王翔 | 周理文 | Post Launch | 2025-07-11 |  | R | R | R |  |  | 无重大安全问题 发运前安全分98.48% | 2025-09-19 | 2025-09-30 | 2025-12-31 | 250296
30030578-EBP | 30030578-2025,AP,XPENG,D01-mirror, assembly. 250297, XT,Equipment | 王保卫 | 陈志斌 | Post Launch | 2025-12-05 |  | R | R | R |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-11-20 | 2025-12-08 | 2026-01-07 | 250297
30030472-EBP | 30030472-2027,EMEA,Mercedes-Benz,MMA-IP,clipping,250293,M,Equipment | 郭正阳 | 刘璟华 | Phase0 | 2025-12-05 |  | R | R | R |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-02-28 | 2026-03-20 | 2026-04-30 | 250293
30030470-EBP | 30030470;2026,AP,BMW,G60 Armrest,Lamination,250292,M,Equipment | 樊皆杰 | 黄琳健 | Phase 5 Production Delivery |  |  | R | R | R |  |  | phase4:90%前侧皮带传送线上料高度超标。 | 2025-09-17 | 2025-09-27 | 2025-10-31 | 250292
30030457-EBP | 30030457-2027,EMEA,Mercedes-Benz,MMA-IP,welding,250294,M,Equipment | 郭正阳 | 郝秀霞 | Phase 2 Concept Definition |  |  | G | G | G |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-05-30 | 2026-06-30 | 2026-08-31 | 250294
30030423-EBP | 30030423;2025,AP,SERES Motors,A15-CNSL, EOL, 250287, M,Equipment | 袁帅 | 王万芳 | Phase 4 Manufacturing Development | 2025-09-12 |  | R | R | R |  |  | 无重大安全问题 发运前安全分82.88% | 2025-10-30 | 2025-11-28 | 2025-12-30 | 250287
30030422-EBP | 30030422;2025,AP,SERES Motors,A15-CNSL, EOL, 250286, M,Equipment | 袁帅 | 黄圣 | Phase 4 Manufacturing Development | 2025-09-12 |  | R | R | R |  |  | 无重大安全问题 发运前安全分84% | 2025-11-14 | 2025-11-28 | 2025-12-30 | 250286
30030421-EBP | 30030421;2025,AP,SERES Motors,A15-CNSL, EOL, 250285, M,Equipment | 袁帅 | 程德宝 | Phase 4 Manufacturing Development | 2025-09-12 |  | R | R | R |  |  | 无重大安全问题 发运前安全分84% | 2025-11-14 | 2025-11-28 | 2025-12-30 | 250285
30030416-EBP | 30030416;2025,AP,JAC-VW,JH-A-sun visor, assy, 250283, T,Equipment | 袁帅 | 周华盛 | Phase 4 Manufacturing Development | 2025-09-24 |  | R | R | R |  |  | 无重大安全问题 发运前安全分97.22% | 2025-10-30 | 2025-11-28 | 2025-12-30 | 250283
30030415-EBP | 30030415;2025,AP,JAC-VW,JH-A-sun visor, assy, 250282, M,Equipment | 袁帅 | 黄定辉 | Phase 4 Manufacturing Development | 2025-09-24 |  | R | R | R | 车间 |  | 无重大安全问题 发运前安全分84.39% | 2025-10-30 | 2025-11-28 | 2025-12-30 | 250282
30030392-EBP | 30030392;2026,AP,Li Auto,X11,EOL,250281,M,Equipment | 尚兵 | 冯全华 | Phase 3 Design Feasibility | 2025-09-25 |  | R | R | R |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-11-30 | 2025-12-19 | 2025-12-30 | 250281
30030390-EBP | 30030390-2026,AP,SERES Motors,F2N sunvisor,Assy,250279，T,Equipment | 孟子冰 | 周华盛 | Phase 5 Production Delivery | 2025-09-24 |  | R | R | R |  |  | 无重大安全问题 发运前安全分94.12% | 2025-10-17 | 2025-11-17 | 2025-12-17 | 250279
30030389-EBP | 30030389;2026,AP,SERES Motors,F2N sunvisor,Assy，250278，M,Equipment | 孟子冰 | 黄定辉 | Phase 4 Manufacturing Development | 2025-09-24 |  | R | R | R | 车间 |  | 无重大安全问题 发运前安全分84.39% | 2025-09-30 | 2025-10-30 | 2025-12-17 | 250278
30030383-EBP | 30030383-2027,AP,Mercedes-Benz,EU V530-CUN,Lamination,250275,T,Equipment | 樊皆杰 | 黄东方 | Phase 4 Manufacturing Development | 2025-09-04 |  | R | R | Y |  |  | phase2：缺少机械资料：黄东方 phase3：缺少机械资料：黄东方 | 2025-09-13 | 2025-10-15 | 2026-05-20 | 250275
30030382-EBP | 30030382-2027,AP,Mercedes-Benz,EU V530 - CUN, glue spray, T,Equipment | 樊皆杰 | 陈志斌 | Phase 4 Manufacturing Development | 2025-11-24 |  | R | R | Y |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-10-31 | 2025-12-30 | 2026-05-20
30030326-EBP | 30030326;2025,AP,XPENG,JH-A-mirror,assy,250270,XT,Equipment | 王保卫 | 陈志斌 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  | 无重大安全问题 发运前安全分85.34% | 2025-10-24 | 2025-11-24 | 2025-12-24 | 250270
30030292-EBP | 30030292-2027,AP,Mercedes-Benz,EU V530-IP,welding,250267,M,Equipment | 樊皆杰 | 郝秀霞 | Phase 4 Manufacturing Development | 2025-09-05 |  | R | R | Y | 车间 |  | 无重大安全问题 发运前安全状态分：81.68% | 2025-09-05 | 2025-09-28 | 2026-05-15 | 250267
30030290-EBP | 30030290-2027,AP,Mercedes-Benz,EU V530-IP, welding, 250266, T,Equipment | 樊皆杰 | 闵宏恩 | Phase 4 Manufacturing Development | 2025-09-18 |  | R | R | Y |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-09-20 | 2025-11-20 | 2026-05-15 | 250266
30030289-EBP | 30030289-2027,AP,Mercedes-Benz,EU V530-IP, welding, 250265, T,Equipment | 樊皆杰 | 高一恒 | Phase 4 Manufacturing Development | 2025-09-25 |  | R | R | Y |  |  | phase2：缺少电气资料：唐兆丰 phase3：缺少电气资料：唐兆丰 | 2025-09-20 | 2025-10-18 | 2026-05-15 | 250265
30030287-EBP | 30030287-2027,AP,Mercedes-Benz,EU V530-IP, welding, 250264, T,Equipment | 樊皆杰 | 闵宏恩 | Phase 5 Production Delivery | 2025-09-24 |  | R | R | R |  |  | phase2：缺少电气资料：齐永安 phase3：缺少电气资料：齐永安 缺少机械资料：闵宏恩 | 2025-10-10 | 2025-10-10 | 2026-04-20 | 250264
30030286-EBP | 30030286-2027,AP,Mercedes-Benz,EU V530-IP, welding, 250263, T,Equipment | 樊皆杰 | 高一恒 | Phase 5 Production Delivery | 2025-09-25 |  | R | R | R |  |  | phase2：缺少电气资料：齐永安 phase3：缺少电气资料：齐永安 | 2025-09-15 | 2025-09-25 | 2026-04-20 | 250263
30030285-EBP | 30030285-2027,AP,Mercedes-Benz,EU V530-IP welding,250262,Y,Equipment | 樊皆杰 | 闵宏恩 | Phase 5 Production Delivery | 2025-09-25 |  | R | R | R |  |  | phase2：缺少电气资料：齐永安 缺少机械资料：闵宏恩 phase3：缺少电气资料：齐永安 | 2025-09-10 | 2025-09-26 | 2026-04-20 | 250262
30030147-EBP | 30030147;2026,AP,SERES Motors,F1L-Sunvisior wrap,250251,T,Equipment | 孟子冰 | 樊爱强 | Phase 4 Manufacturing Development | 2025-08-15 |  | R | R | R |  |  | 无重大安全问题 发运前安全状态分：96.55% | 2025-11-12 | 2025-11-13 | 2026-01-15 | 250251
30030139-EBP | 30030139;2025,AP,Chery,T13C-IP, assy, 250253, M,Equipment | 袁帅 | 李彦辰 | Phase 5 Production Delivery | 2025-09-03 |  | R | R | R |  |  | 线体的电气未装配完成，安全功能未调试完成。分数40% | 2025-09-15 | 2025-09-30 | 2025-12-31 | 250253
30029923-EBP | 30029923-2026,AP,Tes,Highland-EOL,250247,T,Equipment | 龚胜超 | 王晓宇 | Phase0 | 2025-08-25 |  | R | R | R |  |  | 无重大安全问题 发运前安全状态分：88.89% | 2025-10-22 | 2025-11-21 | 2026-02-28 | 250247
30029921-EBP | 30029921-2026,AP,Tes,Highland-FC, Assembly,250246,M,Equipment | 龚胜超 | 李彦辰 | Phase 3 Design Feasibility | 2025-08-25 |  | R | G | G |  |  | 无重大安全问题 发运前安全状态分：90.48% | 2025-10-22 | 2026-06-03 | 2026-06-10 | 250246
30029826-EBP | 30029826-2026,AP,SERES Motors,F1L-Sun visor,Assy,250242,T,Equipment | 孟子冰 | 黄定辉 | Phase 5 Production Delivery | 2025-09-24 |  | R | R | R |  |  | 无重大安全问题 发运前安全分93.1% | 2025-10-18 | 2025-11-20 | 2025-12-05 | 250242
30029700-EBP | 30029700-2026,AP,BMW,NCAR-IP,Clipping,250238,T,Equipment | 杨阳 | 金宇隆 | Phase 4 Manufacturing Development | 2025-09-04 |  | B | R | G |  |  | phase2：100% phase3：100% | 2025-10-15 | 2025-10-31 | 2026-05-31 | 250238
30029699-EBP | 30029699-2026,AP,BMW,NCAR-IP,Clipping,250237,M,Equipment | 杨阳 | 郝秀霞 | Phase 4 Manufacturing Development | 2025-08-28 |  | R | R | G |  |  | phase2：100% phase3：100% | 2025-10-15 | 2025-10-31 | 2026-05-31 | 250237
30029653-EBP | 30029653;2025,AP,SERES Motors,F1L-Sun visor,Assy,250232,T,Equipment | 孟子冰 | 黄定辉 | Phase 4 Manufacturing Development | 2025-05-08 |  | R | R | R |  |  | 无重大安全问题 发运前安全状态分：90% | 2025-09-30 | 2025-09-30 | 2025-12-11 | 250232
30029639-EBP | 30029639;2025,AP,Brilliance-BMW,Ncar-light,assemble,250227,XT,Equipment | 王保卫 | 陈志斌 | Phase 4 Manufacturing Development | 2025-09-22 |  | R | R | R |  |  | 无重大安全问题 发运前安全分97.06% | 2025-11-20 | 2025-11-30 | 2025-12-15 | 250227
30029605-EBP | 30029605;2025,AP,SAIC-VW,ITC-Slash automation, 250230, M,Equipment | 邱伯超 | 王万芳 | Phase Out | 2025-12-05 |  | B | R | R |  |  | PHASE3:缺少电气资料：周光辉 缺少机械资料：王万芳 PHASE4:缺少制造资料：陈帅 | 2025-08-10 | 2025-08-24 | 2025-09-20 | 250230
30029385-EBP | 30029385-2026,AP,General Motors,L234-IP,Assembly,250239,M,Equipment | 龚胜超 | 韦少官 | Phase0 | 2025-08-12 |  | R | R | R |  |  | 无重大安全问题 发运前安全分86.73% | 2025-11-11 | 2025-11-20 | 2025-11-22 | 250239
30029284-EBP | 30029284-2026,AP,SAIC-VW,VW316-9-IP,Automation,250219,M,Equipment | 夏阳 | 郝秀霞 | Phase 1 Quotation | 2025-07-21 |  | R | G | G | 车间 |  | 无重大安全问题 设计自评后复合打分100% | 2025-05-31 | 2026-06-30 | 2026-07-31 | 250219
30029155-EBP | 30029155;2025,AP,General Motors,WL-DP,Lamination,250228,T,Equipment | 龚胜超 | 张帅 | Phase 4 Manufacturing Development | 2025-07-17 |  | R | R | R |  |  | 无重大安全问题 发运前安全分93.75% | 2025-10-29 | 2025-11-06 | 2025-12-06 | 250228
30029017-EBP | 30029017-2026,AP,M Auto,M0301-CNSL,Welding,250201,2T,Equipment | 夏阳 | 黄圣 | Phase 5 Production Delivery | 2025-07-03 |  | R | R | R | 车间 |  | 无重大安全问题 设计自评后复合打分100% | 2025-11-30 | 2026-03-15 | 2026-03-31 | 250201
30028998-EBP | 30028998-2026,AP,Tes,T6-DAB, Lamination, 250212,T,Equipment | 邹成成 | 高一恒 | Phase 5 Production Delivery | 2025-08-05 |  | B | R | R |  |  | 无重大安全问题 发运前安全分91.43% 缺少电气资料——齐永安 | 2025-08-17 | 2025-08-31 | 2025-12-14 | 250212
30028997-EBP | 30028997-2026,AP,Tes,T6-DAB, Lamination, 250211, M,Equipment | 邹成成 | 黄琳健 | Phase 5 Production Delivery | 2025-08-05 |  | R | R | R | 车间 |  | 无重大安全问题 发运前安全分89.29% | 2025-07-31 | 2025-08-31 | 2025-12-14 | 250211
30028984-EBP | 30028984;2027,AP,Audi FAW NEV,Au59x PA-DP,Welding,250206,T,Equipment | 赵军 | 刘璟华 | Phase 4 Manufacturing Development | 2025-07-23 |  | B | B | R |  |  | / | 2025-08-15 | 2025-09-19 | 2025-12-31 | 250206
30028983-EBP | 30028983;2027,AP,Audi FAW NEV,Au59x PA-DP,Welding,250205,T,Equipment | 赵军 | 金宇隆 | Phase 4 Manufacturing Development | 2025-07-23 |  | B | B | R |  |  | 无重大安全问题 发运前安全分96.97% | 2025-08-31 | 2025-09-26 | 2025-12-26 | 250205
30028981-EBP | 30028981;2027,AP,Audi FAW NEV,Au40x PA-DP,Welding,250204,T,Equipment | 赵军 | 刘璟华 | Phase 4 Manufacturing Development | 2025-07-23 |  | B | B | R |  |  | 无重大安全问题 发运前安全分83.33 | 2025-08-31 | 2025-09-26 | 2025-12-15 | 250204
30028939-EBP | 30028939;2025,AP,XPENG,G01-Vent,EOL,250200,M,Equipment | 王翔 | 冯全华 | Phase Out | 2025-08-14 |  | R | R | R |  |  | phase2：100% 静音房 | 2025-09-12 | 2025-09-19 | 2025-10-31 | 250200
30028824-EBP | 30028824;2025,AP,SVW,AU516-Vent,EOL,250197,T,Equipment | 王翔 | 周理文 | Phase 5 Production Delivery | 2025-08-27 |  | R | R | R |  | R | 无重大安全问题 发运前安全分93.33% | 2025-09-09 | 2025-09-26 | 2025-11-30 | 250197
30028776-EBP | 30028776-2027,EMEA,Mercedes-Benz,W244-IP,Punching,250195,M,Equipment | 郭正阳 | 李彦辰 | Terminated |  |  | R | R | R |  |  | 100% | 2025-12-30 | 2025-12-31 | 2026-02-28 | 250195
30028745-EBP | 30028745;2025,AP,VW Anhui,painting line,250192,M,Equipment | 邱伯超 |  | Cancel/Pending |  |  | R | R | R |  |  | 取消 | 2025-07-22 | 2025-07-30 | 2025-10-15 | 250192
30028728-EBP | 30028728-2025,AP,smartmi,MX11-DAB,Lamination.250190,T,Equipment | 邹成成 | 郭新杰 | Phase 2 Concept Definition |  |  | G | G | G |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-06-30 | 2026-07-31 | 2026-10-31 | 250190
30028727-EBP | 30028727-2025,AP,smartmi,MX11-DAB,Lamination,250189,M,Equipment | 邹成成 | 黄琳健 | Phase 4 Manufacturing Development | 2025-07-10 |  | B | R | G |  |  | phase3： 缺少电气资料——齐永安 | 2025-07-15 | 2025-09-15 | 2026-06-30 | 250189
30028719-EBP | 30028719-2025,AP,smartmi,MX11-DAB,Lamination,250188,T,Equipment | 邹成成 | 金宇隆 | Phase 4 Manufacturing Development | 2026-02-24 |  | R | R | G |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-03-15 | 2026-04-15 | 2026-06-30 | 250188
30028718-EBP | 30028718-2025,AP,smartmi,MX11-DAB,Lamination,250187,M,Equipment | 邹成成 | 黄琳健 | Phase 4 Manufacturing Development | 2025-07-11 |  | B | R | G | 车间 |  | phase2： 缺少电气资料——齐永安 phase3： 缺少电气资料——齐永安 | 2025-07-15 | 2025-09-15 | 2026-06-30 | 250187
30028717-EBP | 30028717-2025,AP,Huawei Anhui,F1L-DAB,Lamination,250188,T,Equipment | 邹成成 | 郭新杰 | Cancel/Pending | 2026-02-11 |  | R | R | R |  | / | 取消 | 2025-06-30 | 2025-07-31 | 2025-11-30 | 250188
30028716-EBP | 30028716-2025,AP,Huawei Anhui,F1L-DAB.Lamination,250187,M,Equipment | 邹成成 | 黄琳健 | Cancel/Pending |  |  | R | R | R |  | / | 取消 | 2025-06-30 | 2025-07-20 | 2025-11-30 | 250187
30028702-EBP | 30028702;2026,NA,Toyota,696D-FC,EOL,250186,T,Equipment | 王翔 | 李彦辰 | Phase 4 Manufacturing Development | 2025-06-30 |  | R | R | R |  | R | 无重大安全问题 发运前安全分86.11% | 2025-09-10 | 2025-09-16 | 2025-12-18 | 250186
30028701-EBP | 30028701;2026,NA,Toyota,696D-FC,Assembling,250185,T,Equipment | 王翔 | 李彦辰 | Phase 4 Manufacturing Development | 2025-06-30 |  | R | R | R |  | R | 无重大安全问题 发运前安全分86.11% | 2025-09-10 | 2025-09-16 | 2025-12-18 | 250185
30028700-EBP | 30028700;2026,NA,Toyota,696D-FC,Assembling,250184,T,Equipment | 王翔 | 李彦辰 | Phase 4 Manufacturing Development | 2025-06-30 |  | R | R | R |  | R | 无重大安全问题 发运前安全分89.47% | 2025-09-10 | 2025-09-16 | 2025-12-18 | 250184
30028591-EBP | 30028591;2026,AP,Li Auto,LAMINATION,250182,T,Equipment | 尚兵 | 黄东方 | Phase 5 Production Delivery |  |  | R | R | R |  |  | 无重大安全问题 发运前安全分100% | 2025-11-13 | 2025-11-21 | 2025-11-28 | 250182
30028582-EBP | 30028582;2026,AP,SAIC-VW,VW416-9,EOL,250177,M,Equipment | 尚兵 | 李彦辰 | Phase 5 Production Delivery | 2025-06-20 |  | B | R | R |  | R | phase3：缺少电气资料：徐天丰 phase4：缺少电气资料：徐天丰 缺少制造资料：潘翼伟 缺少质量检查表：李小虎 | 2025-06-22 | 2025-07-13 | 2025-08-24 | 250177
30028578-EBP | 30028578;2026,AP,Li Auto,W04,Lamination,250181,T,Equipment | 尚兵 | 黄东方 | Phase 5 Production Delivery | 2025-12-23 |  | B | R | R |  | R | phase3：自评没有完成：黄东方 phase4：缺少制造资料：佴庆翔 缺少质量检查表：李小虎 | 2025-06-29 | 2025-07-13 | 2025-08-24 | 250181
30028577-EBP | 30028577-2026,AP,Li Auto,W04,Lamination,250180,M,Equipment | 尚兵 | 黄琳健 | Phase 5 Production Delivery |  |  | R | R | R |  |  | 无重大安全问题 发运前安全分100% | 2025-11-22 | 2025-11-25 | 2025-11-30 | 250180
30028576-EBP | 30028576;2026,AP,Li Auto,W04,Lamination,250179,M,Equipment | 尚兵 | 黄琳健 | Phase 5 Production Delivery | 2025-06-03 |  | B | R | R |  | R | phase3：缺少电气资料：巩彦荣 缺少机械资料：黄琳健 phase4： 缺少机械资料：黄琳健 缺少制造资料：佴庆翔 | 2025-06-29 | 2025-07-06 | 2025-08-16 | 250179
30028535-EBP | 30028535-2027,AP,Audi FAW NEV,AU40x PA-DP,Lami,250169,T,Equipment | 赵军 | 周华盛 | Phase 5 Production Delivery | 2025-06-10 |  | B | R | R |  |  | 无重大安全问题 发运前安全分87.3% | 2025-08-28 | 2025-09-28 | 2026-03-19 | 250169
30028534-EBP | 30028534-2027,AP,Audi FAW NEV,AU40x PA-DP,Lami,250168,T,Equipment | 赵军 | 周华盛 | Phase 5 Production Delivery | 2025-06-11 |  | B | R | R |  |  | 无重大安全问题 发运前安全分87.3% | 2025-08-28 | 2025-09-28 | 2026-03-18 | 250168
30028533-EBP | 30028533-2027,AP,Audi FAW NEV,AU40x PA-DP,Lami,250167,M,Equipment | 赵军 | 黄琳健 | Phase 5 Production Delivery | 2025-09-05 |  | R | R | R |  |  | 无重大安全问题 发运前安全分88.71% | 2025-08-01 | 2025-09-19 | 2026-03-12 | 250167
30028524-EBP | 30028524-2027,AP,Audi FAW NEV,AU40x PA-DP,Lami,250166,M,Equipment | 赵军 | 黄琳健 | Phase 5 Production Delivery |  |  | B | R | R |  |  | 无重大安全问题 发运前安全分88.89% | 2025-07-18 | 2025-09-28 | 2026-03-18 | 250166
30028467-EBP | 30028467-2026,AP,SERES Motors,F1L-Sun visor,Assy,250158,T,Equipment | 孟子冰 | 黄定辉 | Phase 5 Production Delivery | 2025-09-24 |  | R | R | R |  | Y | 无重大安全问题 100% | 2025-11-11 | 2025-11-11 | 2025-11-11 | 250158
30028466-EBP | 30028466-2026,AP,SERES Motors,F1L-Sun visor,Assy,250157,M,Equipment | 孟子冰 | 黄定辉 | Phase 5 Production Delivery | 2025-09-24 |  | R | R | R |  | Y | 无重大安全问题 100% | 2025-11-12 | 2025-11-12 | 2025-11-12 | 250157
30028374-EBP | 30028374;2025,AP,Tes,E41-U-Panel,Lamination,250154,T,Equipment | 郭正阳 | 金宇隆 | Phase 4 Manufacturing Development | 2025-08-14 |  | R | R | R |  |  | phase2： 缺少电气资料——徐义星 phase3：（金宇隆）自评 | 2025-09-20 | 2025-09-30 | 2025-12-30 | 250154
30028373-EBP | 30028373-2025,AP,Tes,E41-Surround,Lamination,250153,T,Equipment | 郭正阳 | 樊爱强 | Phase 5 Production Delivery | 2025-08-15 |  | R | R | R |  |  | phase2： 缺少电气资料——徐义星 phase3：等待领导审核：谢懿颖 | 2025-08-30 | 2025-09-30 | 2025-12-30 | 250153
30028295-EBP | 30028295;2026,AP,Brilliance-BMW,G78-HUD,lamination,250148,T,Equipment | 袁帅 | 闵宏恩 | Phase 4 Manufacturing Development | 2025-06-16 |  | B | B | R |  | B | / | 2025-06-30 | 2025-07-30 | 2025-12-31 | 250148
30028292-EBP | 30028292;2025,AP,Geely,X2411,Lamination,250147,M,Equipment | 尚兵 | 陈洁 | Phase 5 Production Delivery | 2025-09-16 |  | R | R | R |  | R | 无重大安全问题 98.55% | 2025-06-08 | 2025-11-06 | 2025-11-13 | 250147
30028259-EBP | 30028259-2026,AP,SERES Motors,F1L-CNSL,Equipment | 夏阳 | 李彦辰 | Phase Out | 2025-05-21 |  | R | R | R |  |  | Phase Out | 2025-11-15 | 2025-11-30 | 2026-03-31
30028147-EBP | 30028147;2025,AP,Leapmotor,D13&P177&DX1H-CNSL,assy,250141,M,Equipment | 夏阳 | 王万芳 | Phase 5 Production Delivery | 2025-05-26 |  | B | B | R |  | / | 无重大安全问题 发运前安全分88.65% | 2025-05-30 | 2025-06-30 | 2025-11-30 | 250141
30028088-EBP | 30028088;2025,AP,SAIC,SHA-DAB, Lamination, 250134, T,Equipment | 邹成成 | 张帅 | Phase 5 Production Delivery | 2025-05-30 |  | R | R | R |  | R | phase2&phase3： 缺少电气资料：齐永安 PDL01398571/A-Equipment Safety Plan Checklist (Electrical) | 2025-05-31 | 2025-06-15 | 2025-10-20 | 250134
30028087-EBP | 30028087;2025,AP,SAIC,SHA-DAB, Lamination, 250133,M,Equipment | 邹成成 | 黄琳健 | Phase 5 Production Delivery |  |  | B | R | R |  | R | PHASE3: 缺少电气资料——齐永安 缺少机械资料——黄琳健 | 2025-05-20 | 2025-05-31 | 2025-10-20 | 250133
30028086-EBP | 30028086;2025,AP,SERES Motors,F1L-DAB, Lamination, 250136, T,Equipment | 邹成成 | 高一恒 | Phase 5 Production Delivery | 2025-06-15 |  | B | B | R |  | R | 缺少制造资料——陈帅 | 2025-05-31 | 2025-06-15 | 2025-10-21 | 250136
30028084-EBP | 30028084;2025,AP,SERES Motors,F1L-DAB, Lamination, 250135, M,Equipment | 邹成成 | 黄琳健 | Phase 5 Production Delivery |  |  | B | R | R |  | R | phase3：等待领导审批——谢懿颍 phase4：缺少制造资料——佴庆翔 缺少质量检查表——高宇辰 | 2025-05-20 | 2025-05-31 | 2025-10-21 | 250135
30028060-EBP | 30028060-2025,AP,XPENG,G01&F1L-mirror,assy,250128,M,Equipment | 王保卫 | 陈志斌 | Post Launch | 2025-07-02 |  | R | R | R |  | R | 无重大安全问题 发运前安全分88.65% | 2025-06-15 | 2025-07-30 | 2025-12-31 | 250128
30028053-EBP | 30028053-2025,AP,XPENG,G01&F1L-mirror,assy,250127,M,Equipment | 王保卫 | 韦少官 | Phase 5 Production Delivery | 2025-07-02 |  | B | R | R |  | G | 缺少电气资料：徐义星 phase4：缺少制造资料：佴庆翔 缺少项目资料：袁帅 | 2025-06-15 | 2025-07-30 | 2025-09-30 | 250127
30028049-EBP | 30028049-2025,AP,XPENG,G01&F1L-mirror,assy,250126,M,Equipment | 王保卫 | 陈志斌 | Phase 5 Production Delivery | 2025-07-02 |  | B | R | R |  | G | 无重大安全问题 发运前安全分88.65% | 2025-06-15 | 2025-07-30 | 2025-11-30 | 250126
30028048-EBP | 30028048-2025,AP,BMW,NA5-IP,EOAT,250121,3T,Equipment | 龚胜超 | 王晓宇 | Phase Out |  |  | B | B | R | 取消 | R | 取消 | 2025-04-21 | 2025-11-06 | 2025-12-31 | 250121
30027969-EBP | 30027969;2025,AP,BYD,BYD-SA3-DP, assembly, 250119, 1M,Equipment | 王保卫 | 王晓宇 | Phase 5 Production Delivery | 2025-12-10 |  | B | B | R |  | G | 缺少制造资料：陈帅 缺少项目资料：王保卫 | 2025-06-20 | 2025-07-20 | 2025-09-20 | 250119
30027944-EBP | 30027944-2025,AP,Chery,EHY-Pillar,Welding,250115,M,Equipment | 夏阳 | 黄圣 | Phase 4 Manufacturing Development | 2025-04-29 |  | R | R | G |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-11-30 | 2025-05-31 | 2026-06-30 | 250115
30027941-EBP | 30027941-2025,AP,Geely Sichuan CV,EX1H-DAB,Lamination,250117,T,Equipment | 邹成成 | 闵宏恩 | Phase 2 Concept Definition |  |  | G | G | G |  |  |  | 2026-12-31 | 2027-01-31 | 2027-02-28 | 250117
30027779-EBP | 30027779-2025,AP,Volvo Group Global,825K-IP, lamination, 250025, 2T,Equipment | 袁帅 | 闵宏恩 | Terminated |  |  | R | R | R |  |  | 项目取消% | 2025-12-26 | 2025-12-26 | 2025-12-26 | 250025
30027739-EBP | 30027739-2025,AP,Ford,U625-DP,Lamination,250109,M,Equipment | 郭正阳 | 高一恒 | Phase Out | 2025-04-21 |  | B | B | B |  |  | 完成 | 2025-05-09 | 2025-07-15 | 2025-10-15 | 250109
30027738-EBP | 30027738-2025,AP,Ford,U625-DP,Lamination,250108,M,Equipment | 郭正阳 | 高一恒 | Phase Out | 2025-04-21 |  | B | B | B |  |  | 完成 | 2025-05-09 | 2025-07-15 | 2025-10-10 | 250108
30027737-EBP | 30027737-2025,AP,Ford,U625-DP,Lamination,250106,M,Equipment | 郭正阳 | 高一恒 | Phase Out | 2025-04-21 |  | B | B | B |  | R | 完成 | 2025-05-09 | 2025-09-30 | 2025-10-15 | 250106
30027736-EBP | 30027736-2025,AP,Ford,U625-DP,Lamination,250105,M,Equipment | 郭正阳 | 高一恒 | Phase Out | 2025-04-21 |  | B | B | B |  |  | 完成 | 2025-05-09 | 2025-07-15 | 2025-10-15 | 250105
30027730-EBP | 30027730-2025,AP,YFITC-Internal,SA5 UFL,250107,T,Equipment | 邱伯超 | 王晓宇 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 缺少机械资料，自评没有完成：王晓宇 | 2025-04-22 | 2025-05-06 | 2025-06-28 | 250107
30027723-EBP | 30027723;2026,AP,Brilliance-BMW,G58-IP,Lamination,250104,T,Equipment | 孟子冰 | 黄东方 | Phase 4 Manufacturing Development |  |  | B | R | R |  | R | 无重大安全问题 发运前安全状态分：88.57% | 2025-05-12 | 2025-05-31 | 2025-12-12 | 250104
30027717-EBP | 30027717;2026,AP,Brilliance-BMW,G58-IP,Lamination,250103,T,Equipment | 孟子冰 | 阚城奔 | Phase 5 Production Delivery | 2025-04-10 |  | B | R | R |  | R | 无重大安全问题 发运前安全分96.55% | 2025-05-12 | 2025-09-25 | 2025-12-03 | 250103
30027693-EBP | 30027693-2025,AP,Tes,HLD-DP,lamination，250096,M,Equipment | 陈佳荣 | 郭新杰 | Post Launch | 2025-06-09 |  | B | R | R |  | R | phase3：缺少电气资料：丁宝强 缺少机械资料：樊爱强 phase4：缺少电气资料：丁宝强 缺少机械资料：樊爱强 缺少制造资料：施正茂 安全打分表责任人错误：陈佳荣 | 2025-05-11 | 2025-06-29 | 2025-08-10 | 250096
30027692-EBP | 30027692-2025,AP,Tes,HLD-DP,lamination。250097，T,Equipment | 陈佳荣 | 郭新杰 | Phase 5 Production Delivery | 2025-06-17 |  | B | R | R |  | R | phase3：缺少电气资料：丁宝强 缺少机械资料：樊爱强 phase4：缺少电气资料：丁宝强 缺少机械资料：樊爱强 缺少制造资料：施正茂 安全打分表责任人错误：陈佳荣 | 2025-05-11 | 2025-06-29 | 2025-08-10 | 250097
30027640-EBP | 30027640-2025,NA,BMW,G45-DP,Wrapping,250093,M,Equipment | 王翔 | 黄琳健 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 无重大安全问题 86.93% | 2025-04-18 | 2025-04-24 | 2026-01-30 | 250093
30027637-EBP | 30027637-2025,NA,BMW,G45-DP, wrapping,250092,T,Equipment | 王翔 | 金宇隆 | Phase 5 Production Delivery |  |  | R | R | R |  | R | 无重大安全问题 96.83% | 2025-05-09 | 2025-05-23 | 2026-01-30 | 250092
30027636-EBP | 30027636-2025,NA,BMW,G45-DP, wrapping,250091,T,Equipment | 王翔 | 金宇隆 | Phase 5 Production Delivery |  |  | R | R | R |  | R | 无重大安全问题 96.83% | 2025-05-09 | 2025-05-23 | 2026-01-30 | 250091
30027611-EBP | 30027611;2025,AP,BYD,SA3-CNSL, assembly, 250076,1M,Equipment | 王保卫 | 李彦辰 | Phase 5 Production Delivery | 2025-04-10 |  | R | R | R |  | R | phase2：缺少机械资料，自评没有完成：李彦辰 phase3：缺少机械资料，自评没有完成：李彦辰 phase4：缺少制造资料：何琳霖 缺少项目资料：王保卫 | 2025-06-20 | 2025-07-20 | 2025-08-31 | 250076
30027610-EBP | 30027610;2025,AP,BYD,SA3-IP, assembly, 250077, 1M,Equipment | 王保卫 | 李彦辰 | Phase 5 Production Delivery | 2025-04-11 |  | R | R | R |  | R | phase2：缺少机械资料，自评没有完成：李彦辰 phase3：缺少机械资料，自评没有完成：李彦辰 phase4：缺少制造资料：何琳霖 缺少项目资料：王保卫 | 2025-06-20 | 2025-07-20 | 2025-08-31 | 250077
30027594-EBP | 30027594-2025,AP,GAC,A29-sun visor,assy,250086,M,Equipment | 孟子冰 | 黄定辉 | Post Launch | 2025-06-11 |  | R | R | R |  | R | 无重大安全问题 发运前安全分96.54% | 2025-09-25 | 2025-09-26 | 2025-11-19 | 250086
30027593-EBP | 30027593-2025,AP,BYD,SA3-DP, assembly, 250085, 1M,Equipment | 王保卫 | 郝秀霞 | Phase 4 Manufacturing Development |  |  | R | R | R |  | R | SSO自评没有完成——郝秀霞 | 2025-06-20 | 2026-01-31 | 2026-02-28 | 250085
30027592-EBP | 30027592-2025,AP,BYD,SA3-DP,assembly, 250084, 1M,Equipment | 王保卫 | 郝秀霞 | Phase 4 Manufacturing Development |  |  | R | R | R |  | R | SSO自评没有完成——郝秀霞 | 2025-06-20 | 2026-01-31 | 2026-02-28 | 250084
30027591-EBP | 30027591-2025,AP,BYD,SA3-DP,assembly, 250083,1M,Equipment | 王保卫 | 郝秀霞 | Phase 4 Manufacturing Development |  |  | R | R | R |  | R | SSO自评没有完成——郝秀霞 | 2025-06-20 | 2026-01-31 | 2026-02-28 | 250083
30027590-EBP | 30027590-2025,AP,BYD,SA3-DP, assembly, 250082, 1M,Equipment | 王保卫 | 郝秀霞 | Phase 4 Manufacturing Development |  |  | R | R | R |  | R | SSO自评没有完成——郝秀霞 | 2025-06-20 | 2026-01-31 | 2026-02-28 | 250082
30027586-EBP | 30027586;2025,AP,BYD,SA3-DP,lamination,250081,1M,Equipment | 王保卫 | 黄琳健 | Phase 5 Production Delivery | 2025-03-21 |  | B | R | R |  | R | phase3：缺少电气资料：徐义星 phase4：缺少项目资料/责任人指派错误：王保卫 | 2025-06-20 | 2025-07-20 | 2025-08-31 | 250081
30027585-EBP | 30027585;2025,AP,BYD,SA3-DP, Lamination, 250080,1M,Equipment | 王保卫 | 黄琳健 | Phase 5 Production Delivery | 2025-03-31 |  | B | R | R |  | R | SSO自评没有完成——黄琳健 | 2025-06-15 | 2025-06-25 | 2025-07-25 | 250080
30027581-EBP | 30027581;2025,AP,Others,other,Granulator,250089,M,Equipment | 樊皆杰 | 程德宝 | Phase 5 Production Delivery |  |  | B | B | R |  | G | 等待领导审批：顾冬 | 2025-04-30 | 2025-05-20 | 2025-08-10 | 250089
30027337-EBP | 30027337;2025,AP,Brilliance-BMW,G78-Vent,EOL,250064,M,Equipment | 王翔 | 冯全华 | Phase Out |  |  | R | R | R |  | R | 100% | 2025-04-25 | 2025-04-28 | 2025-10-31 | 250064
30027253-EBP | 30027253;2025,AP,Geely,HS11-light,welding,250061,M,Equipment | 陈佳荣 | 韦少官 | Post Launch |  |  | B | B | R |  | R | 缺少制造资料：——潘翼伟 PDL01356993/A-Equipment & Tooling Assembly Process Form PDL01356990/A-Process Failure Mode & Effects Analysis | 2025-04-06 | 2025-04-27 | 2025-05-31 | 250061
30027220-EBP | 30027220;2025,AP,SERES Motors,F2,Roller glue,250059,M,Equipment | 孟子冰 | 陈洁 | Phase 5 Production Delivery |  |  | B | B | R |  | Y | 无重大安全问题 73.17% | 2025-04-18 | 2025-04-23 | 2025-11-13 | 250059
30027112-EBP | 30027112;2026,AP,BMW,G68 LCI-IP,US Welding,250057,T,Equipment | 杨阳 | 刘璟华 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 无重大安全问题 发运前安全分96.97% | 2025-03-31 | 2025-04-30 | 2025-11-30 | 250057
30027111-EBP | 30027111;2026,AP,BMW,G68 LCI-IP,US Welding,250056,T,Equipment | 杨阳 | 刘璟华 | Phase 5 Production Delivery |  |  | B | B | R |  | G | 无重大安全问题 发运前安全分93.94% | 2025-03-31 | 2025-05-31 | 2025-11-30 | 250056
30027110-EBP | 30027110;2026,AP,BMW,G68 LCI-IP,US Welding,250055,M,Equipment | 杨阳 | 黄圣 | Phase 5 Production Delivery |  |  | B | B | R | 利旧G60焊机 | G | 无重大安全问题 发运前安全分88.48% | 2025-03-31 | 2025-05-31 | 2025-11-30 | 250055
30026497-EBP | 30026497;2025,AP,Daimler,X540 MF,lamination RR,240280,T#2,Equipment | 白宇鹏 | 郭新杰 | Phase 5 Production Delivery | 2025-04-11 |  | R | R | R |  | R | phase2：SSO自评没有完成——郭新杰 phase3：SSO自评没有完成——郭新杰 | 2025-05-06 | 2025-06-22 | 2025-07-12 | 240280
30026496-EBP | 30026496;2025,AP,Daimler,X540 MF,laminaton RL,240279,T#2,Equipment | 白宇鹏 | 郭新杰 | Phase 5 Production Delivery | 2025-06-16 |  | R | R | R |  | R | 缺少机械资料：——郭新杰 PDL01342497/A-Equipment Safety Plan Checklis (Mechanical) SSO自评没有完成——郭新杰 | 2025-05-06 | 2025-06-22 | 2025-07-12 | 240279
30026495-EBP | 30026495;2025,AP,Daimler,X540 MF,lamination FR,240278,T#2,Equipment | 白宇鹏 | 张帅 | Phase 5 Production Delivery | 2025-06-18 |  | R | R | R |  | R | phase2：SSO自评没有完成——张帅 phase3：SSO自评没有完成——张帅 phase4：缺少质量检查表——高宇辰 | 2025-05-16 | 2025-06-20 | 2025-07-18 | 240278
30026493-EBP | 30026493;2025,AP,Daimler,X540-MF,lamination FL,240277,T#2,Equipment | 白宇鹏 | 张帅 | Phase 5 Production Delivery | 2025-06-18 |  | B | R | R |  | R | SSO自评没有完成——张帅 | 2025-05-16 | 2025-06-20 | 2025-07-06 | 240277
30026136-EBP | 30026136-2026,AP,Mercedes-Benz,V520,CUN,Welding,250048,T,Equipment | 尚兵 | 刘璟华 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 缺少发运前安全检查：刘聪 缺少制造资料：马品将 | 2025-03-29 | 2025-04-19 | 2025-06-28 | 250048
30026135-EBP | 30026135;2026,AP,Mercedes-Benz,V520,IP,Welding,250047,T,Equipment | 尚兵 | 刘璟华 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 缺少质量检查表——李小虎 SSO自评没有完成：高大尉 | 2025-04-30 | 2025-05-30 | 2025-06-15 | 250047
30026096-EBP | 30026096-2025,AP,Tes,T0402-IP,Automation,250043,M,Equipment | 邹成成 | 王晓宇 | Post Launch |  |  | B | B | R | 线体较简单，无利旧价值 | R | phase4：缺少制造资料：陈帅 缺少质量检查表：李小虎 | 2025-03-22 | 2025-05-25 | 2025-09-21 | 250043
30026089-EBP | 30026089-2025,AP,Huawei Anhui,C71-DAB,Lamination,250033,T,Equipment | 邹成成 | 金宇隆 | Phase 5 Production Delivery | 2025-12-23 |  | B | B | R |  | R | 缺少电气资料：古亮 缺少制造资料：陈帅 | 2025-03-08 | 2025-03-31 | 2025-09-14 | 250033
30026088-EBP | 30026088-2025,AP,Tes,T0402-IP, Automation. 250042,M,Equipment | 邹成成 | 王晓宇 | Post Launch |  |  | B | B | B |  | Y | / | 2025-02-26 | 2025-03-31 | 2025-07-20 | 250042
30026087-EBP | 30026087-2025,AP,Tes,T0402-IP, Automation, 250041,M,Equipment | 邹成成 | 王晓宇 | Post Launch |  |  | B | B | B |  | Y | / | 2025-02-26 | 2025-03-31 | 2025-07-20 | 250041
30026044-EBP | 30026044;2026,AP,Mercedes-Benz,V520 Lower-DP,250036,T,Equipment | 尚兵 | 阚城奔 | Phase 5 Production Delivery |  |  | B | R | R |  | R | phase3缺少领导审批——谢懿颖 phase4缺少电气资料——王一飞 缺少质量检查表——高宇辰 | 2025-03-15 | 2025-04-30 | 2025-06-12 | 250036
30026043-EBP | 30026043;2025,AP,Mercedes-Benz,V520-DP,Lamination,250035,T,Equipment | 尚兵 | 陈子翌 | Phase 5 Production Delivery |  |  | B | B | B |  | B | 完成 | 2025-04-23 | 2025-04-30 | 2025-09-20 | 250035
30026042-EBP | 30026042;2026,AP,BMW,G60 LCI-IP,US Welding,250032,T,Equipment | 杨阳 | 刘璟华 | Phase 5 Production Delivery | 2025-03-11 |  | B | R | R |  | R | 无重大安全问题 93.94% | 2025-04-30 | 2025-08-31 | 2025-11-30 | 250032
30026041-EBP | 30026041;2026,AP,BMW,G60 LCI-IP,US Welding,250031,T,Equipment | 杨阳 | 刘璟华 | Phase 5 Production Delivery | 2025-03-20 |  | B | R | R |  | R | 利旧，设备在欧洲现场 | 2025-04-30 | 2025-08-31 | 2025-11-30 | 250031
30026040-EBP | 30026040;2026,AP,BMW,G60 LCI-IP,HS Welding,250030,T,Equipment | 杨阳 | 刘璟华 | Phase 5 Production Delivery | 2025-04-21 |  | B | R | R |  | G | 利旧，设备在欧洲现场 | 2025-04-30 | 2025-08-31 | 2025-11-30 | 250030
30026039-EBP | 30026039;2026,AP,BMW,G60 LCI-IP,US Welding,250029,M,Equipment | 杨阳 | 黄圣 | Phase 5 Production Delivery | 2025-02-19 |  | B | R | R | 利旧 | G | 利旧，设备在欧洲现场 | 2025-05-31 | 2025-08-31 | 2025-11-30 | 250029
30026038-EBP | 30026038;2026,AP,BMW,G60 LCI-IP,HS Welding,250028,M,Equipment | 杨阳 | 黄圣 | Phase 5 Production Delivery | 2025-02-19 |  | B | B | R | 利旧 | G | 利旧，设备在欧洲现场 | 2025-05-31 | 2025-08-31 | 2025-11-30 | 250028
30026036-EBP | 30026036-2026,AP,Volvo Group Global,825K-IP, lamination, 250024, 2T,Equipment | 袁帅 | 李华 | Terminated |  |  | R | R | R | 暂停 | / | 100% | 2025-03-28 | 2025-06-27 | 2025-10-31 | 250024
30026035-EBP | 30026035-2026,AP,Volvo Group Global,825K-IP, lamination, 250023, M,Equipment | 袁帅 | 陈洁 | Terminated |  |  | B | G | G | 备件（利旧） | Y | 缺少机械资料：——陈洁 PDL01327823/A-Equipment Safety Plan Checklis (Mechanical)新版 PDL01327855/A-Design Failure Mode & Effects Analysis | 2025-03-28 | 2026-12-30 | 2026-12-30 | 250023
30026034-EBP | 30026034-2026,AP,Volvo Group Global,825K-IP, Infrared, 250022, 2T,Equipment | 袁帅 | 周华盛 | Terminated |  |  | B | G | G |  | R | / | 2026-12-30 | 2026-12-30 | 2026-12-30 | 250022
30026033-EBP | 30026033-2026,AP,Volvo Group Global,825K-IP, Infrared, 250021, 2T,Equipment | 袁帅 | 周华盛 | Terminated |  |  | B | R | R |  | G | 项目取消% | 2025-12-26 | 2025-12-26 | 2025-12-26 | 250021
30026032-EBP | 30026032-2026,AP,Volvo Group Global,825K-IP, Infrared, 250020, M,Equipment | 袁帅 | 黄圣 | Terminated |  |  | R | R | R | 备件（利旧） | R | 项目取消% | 2025-12-26 | 2025-12-26 | 2025-12-26 | 250020
30025746-EBP | 30025746-2026,AP,Mercedes-Benz,V40-DP,Lami,250006,1T,Equipment | 夏阳 | 高一恒 | Phase 4 Manufacturing Development |  |  | B | B | R |  | R | 无重大安全问题 发运前安全分89.19% | 2025-02-28 | 2025-04-30 | 2026-03-31 | 250006
30025745-EBP | 30025745-2026,AP,Mercedes-Benz,V540-DP,Lami,250005,1T,Equipment | 夏阳 | 高一恒 | Phase 4 Manufacturing Development |  |  | B | B | R |  | R | / | 2025-02-28 | 2025-04-30 | 2026-03-31 | 250005
30025718-EBP | 30025718;2026,AP,M Auto,MS12,Fixing,250015,T,Equipment | 尚兵 | 陈雨杭 | Phase 5 Production Delivery |  |  | B | B | R |  | Y | 缺少电气资料：——王一飞 缺少制造资料：施正茂 缺少质量检查表：高宇辰 | 2025-03-22 | 2025-03-28 | 2025-07-20 | 250015
30025717-EBP | 30025717;2026,AP,M Auto,MS12,Fixing,250014,M,Equipment | 尚兵 | 黄琳健 | Phase 5 Production Delivery |  |  | B | R | R |  | R | phase3：缺少电气资料：——王一飞 PDL01333231/A-Control Logic Diagram of Safety System PDL01333243/A-Safety Functions Evaluation of Machine phase4：缺少电气资料：——王一飞 缺少质量检查表：高宇辰 | 2025-03-22 | 2025-04-26 | 2025-07-20 | 250014
30025716-EBP | 30025716;2026,AP,M Auto,MX11,Fixing,250013,T,Equipment | 尚兵 | 金宇隆 | Cancel/Pending |  |  | R | R | R |  | / |  | 2025-03-22 | 2025-04-22 | 2025-05-22 | 250013
30025715-EBP | 30025715;2026,AP,M Auto,MX11,Fixing,250012,M,Equipment | 尚兵 | 陈洁 | Cancel/Pending |  |  | R | R | R |  | / |  | 2025-03-08 | 2025-03-31 | 2025-05-22 | 250012
30025688-EBP | 30025688;2025,AP,BYD,HA5-DP,lamination，250008,T,Equipment | 陈佳荣 | 黄琳健 | Post Launch |  |  | B | B | B |  | R | / | 2025-03-02 | 2025-03-16 | 2025-04-20 | 250008
30025686-EBP | 30025686-2025,AP,M Auto,MX11,glue spray,250007,T,Equipment | 尚兵 | 周理文 | Phase Out |  |  | B | B | R |  | R | 缺少质量检查表——高宇辰 PDL01316449/A-Equipment Process Quality Inspection Form | 2025-02-28 | 2025-03-09 | 2025-04-26 | 250007
30025636-EBP | 30025636;2025,AP,Brilliance-BMW,Ncar-lght,assemble,240292,T,Equipment | 陈佳荣 | 陈志斌 | Post Launch |  |  | B | B | R |  | R | 无重大安全问题 发运前安全分97.83% | 2025-02-28 | 2025-03-23 | 2025-11-22 | 240292
30025515-EBP | 30025515;2025,AP,Geely-Volvo,v44x,torque fixture,250001,T,Equipment | 尚兵 | 杜全喆 | Phase 5 Production Delivery |  |  | B | B | B |  | B | 项目经理与业务和设计确认，此项目不适用XSO. | 2025-01-14 | 2025-01-21 | 2025-11-30 | 250001
30025241-EBP | 30025241-2026,AP,BMW,G60-DP,Wedling,240289,T,Equipment | 杨阳 | 刘璟华 | Phase 5 Production Delivery |  |  | B | R | R |  | R | 无重大安全问题 发运前安全分97.22% | 2025-03-08 | 2025-05-31 | 2025-11-30 | 240289
30025240-EBP | 30025240-2026,AP,BMW,G60-DP,Welding,240288,M,Equipment | 杨阳 | 郝秀霞 | Phase 5 Production Delivery |  |  | B | R | R |  | R | 无重大安全问题 发运前安全分79.87% | 2025-03-08 | 2025-05-31 | 2025-11-30 | 240288
30025192-EBP | 30025192-2027,EMEA,BMW,G60 LCI ArExtension,Lam,240286,T,Equipment | 郭正阳 | 闵宏恩 | Phase Out | 2025-01-24 |  | B | B | R |  | G | 无重大安全问题 发运前安全分100% | 2025-07-15 | 2025-07-30 | 2026-02-28 | 240286
30025127-EBP | 30025127;2025,AP,SERES Motors,F3-CNSL,Lamination，240283,M,Equipment | 陈佳荣 | 黄琳健 | Post Launch |  |  | B | B | B |  | R | / | 2025-01-12 | 2025-02-16 | 2025-03-16 | 240283
30025118-EBP | 30025118-2025,AP,SERES Motors,F3-lamp，assemble，240281，T,Equipment | 陈佳荣 | 韦少官 | Post Launch |  |  | B | B | B |  | R | 完成 | 2025-03-09 | 2025-03-16 | 2025-06-30 | 240281
30025074-EBP | 30025074;2025,AP,Daimler,X540UBL-Glue spray,240276,T,Equipment | 白宇鹏 | 陈志斌 | Phase Out |  |  | B | B | R |  | R | 缺少制造资料：——何琳霖 PDL01243133/A-Process Failure Mode & Effects Analysis PDL01243136/A-Equipment & Tooling Assembly Process Form 缺少机械资料：——陈志斌 PDL01289221/A-Special Characteristics List PDL01289244/A-Basic Assessment Ergonomics PDL01289245/A-Drawings/CAD PDL01289246/A-Design Failure Mode & Effects Analysis PDL01289248/A-Equipment Risk/Safety Assessment PDL01289262/A-Delivery Documentation | 2025-03-14 | 2025-04-18 | 2025-05-30 | 240276
30025073-EBP | 30025073;2025,AP,Daimler,X540UBL-Glue spray,240275,M,Equipment | 白宇鹏 | 陈志斌 | Phase Out |  |  | B | B | B |  | R | / | 2025-01-24 | 2025-03-21 | 2025-05-16 | 240275
30024632-EBP | 30024632-2025,EMEA,Mercedes-Benz,H244-IP,Welding,240263,T,Equipment | 郭正阳 | 刘璟华 | Phase0 | 2024-11-12 |  | R | R | R |  | R | phase2：自评未完成——高大尉 phase3：缺少机械资料：——高大尉 phase4：缺少机械资料：——高大尉 | 2025-12-29 | 2025-12-30 | 2026-01-30 | 240263
30024544-EBP | 30024544-2026,AP,Mercedes-Benz,V540-DP,TS,240267,1T,Equipment | 夏阳 | 张帅 | Phase 4 Manufacturing Development |  |  | B | B | R |  | R | / | 2025-01-13 | 2025-02-28 | 2026-03-31 | 240267
30024543-EBP | 30024543-2026,AP,Mercedes-Benz,V540-IP,CUN,240268,1T,Equipment | 夏阳 | 陈子翌 | Phase 5 Production Delivery |  |  | B | B | R |  | B | 无重大安全问题 发运前安全分93.33% | 2025-02-10 | 2025-03-13 | 2026-04-30 | 240268
30024378-EBP | 30024378;2025,AP,General Motors,L234-FC,lamination,240260,T,Equipment | 王保卫 | 韦少官 | Phase Out | 2025-03-28 |  | B | B | R |  | R | 100% | 2025-02-28 | 2025-07-31 | 2025-10-31 | 240260
30024359-EBP | 30024359-2025,AP,Brilliance-BMW,Ncar-lgiht,240255,assemble，M,Equipment | 陈佳荣 | 冯全华 | Phase 5 Production Delivery | 2025-12-05 | 震动箱周边缝隙小于20mm | B | B | R | BMW EOL线体 维修们安全门锁ECPL 换模双手按钮 切板机进料无光栅，客户确认 震动箱周边缝隙小于20mm | R | 缺少电气资料：姚澳华 缺少质量检查表：李小虎 | 2024-11-24 | 2025-01-19 | 2025-06-29 | 240255
30024307-EBP | 30024307;2025,AP,SAIC-VW,KDB23-PAB, Lamination, 240257, T,Equipment | 邹成成 | 朱聪 | Post Launch |  |  | B | B | B |  | B | 完成 | 2024-11-30 | 2024-12-15 | 2025-01-15 | 240257
30024289-EBP | 30024289;2025,AP,Brilliance-BMW,Ncar-light,assemble,240256,M,Equipment | 陈佳荣 | 冯全华 | Phase 5 Production Delivery | 2025-09-16 |  | R | R | R |  |  | 无重大安全问题 发运前安全分76.71% | 2025-11-21 | 2025-11-28 | 2025-12-05 | 240256
30024279-EBP | 30024279;2025,AP,Brilliance-BMW,Ncar-light，assemble，240255,M,Equipment | 陈佳荣 | 冯全华 | Cancel/Pending |  |  | R | R | R | 遗留 | / |  | 2024-11-10 | 2024-11-30 | 2025-02-10 | 240255
30024236-EBP | 30024236;2025,AP,SERES Motors,F3-DAB, Lamination, 240253, T,Equipment | 邹成成 | 周华盛 | Post Launch |  |  | B | B | B | / | R | / | 2024-12-08 | 2025-02-28 | 2025-03-31 | 240253
30024235-EBP | 30024235;2025,AP,SERES Motors,F3-DAB, lamination. 240252, M,Equipment | 邹成成 | 黄琳健 | Post Launch |  |  | B | B | B |  | R | SSO自评未完成——黄琳健 | 2024-11-15 | 2024-11-23 | 2025-02-22 | 240252
30024202-EBP | 30024202-2024,AP,Tes,T0402-CNSL_AUT ASS,240250,1M,Equipment | 邱伯超 | 王万芳 | Phase Out |  |  | B | B | B |  | B | 完成 | 2024-11-15 | 2024-12-10 | 2025-02-15 | 240250
30024185-EBP | 30024185-2024,AP,Tes,T0402-CNSL_AUT ASS,240249,1M,,Equipment | 李忆陵 | 李彦辰 | Phase Out |  | 区域扫描仪选择了非安全型，扫描区域可能存在干涉，已确认是客户要求的型号。 | B | B | B |  | B | 完成 | 2024-10-30 | 2024-11-15 | 2025-01-24 | 240249
30024170-EBP | 30024170;2026,AP,Daimler,W520-UBL,glue spray,240246,T,Equipment | 白宇鹏 | 陈志斌 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 缺少制造资料：——何琳霖 PDL01243133/A-Process Failure Mode & Effects Analysis PDL01243136/A-Equipment & Tooling Assembly Process Form | 2024-11-28 | 2024-12-29 | 2025-05-30 | 240246
30024169-EBP | 30024169;2026,AP,Daimler,W520-UBL,glue spray,240245,M,Equipment | 白宇鹏 | 陈志斌 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 自评没有完成——陈志斌 | 2024-11-28 | 2024-12-29 | 2025-05-30 | 240245
30024154-EBP | 30024154-2026,AP,Daimler,W520-UBL,lamination,240211,T#2,Equipment | 白宇鹏 | 樊爱强 | Post Launch |  |  | B | B | R |  | R | 缺少制造资料：朱建灯 缺少质量检查表：唐红芳 | 2025-03-21 | 2025-04-18 | 2026-02-28 | 240211
30024153-EBP | 30024153;2026,AP,Daimler,W520-UBL,lamination,240210,T#1,Equipment | 白宇鹏 | 樊爱强 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 缺少制造资料：——朱建灯 PDL01243133/A-Process Failure Mode & Effects Analysis PDL01243136/A-Equipment & Tooling Assembly Process Form 自评没有完成——樊爱强 | 2024-12-06 | 2024-12-27 | 2025-05-30 | 240210
30024152-EBP | 30024152;2026,AP,Daimler,W520-UBL,lamination,240209,M,Equipment | 白宇鹏 | 陈斌 | Phase 5 Production Delivery |  |  | B | B | R | / | R | 项目经理未指派任务：——白宇鹏 PDL01241985/A-Equipment Safety Status Checklist 缺少机械资料：——陈斌 PDL01241926/A-Special Characteristics List PDL01241990/A-Basic Assessment Ergonomics PDL01241995/A-Drawings/CAD PDL01241996/A-Design Failure Mode & Effects Analysis PDL01242002/A-Equipment Risk/Safety Assessment SSO自评未完成——陈斌 | 2024-11-26 | 2024-12-27 | 2025-05-30 | 240209
30024151-EBP | 30024151;2026,AP,Daimler,W520-MF,lamination RR,240208,Equipment | 白宇鹏 | 金宇隆 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 自评没有完成——金宇隆 | 2024-11-15 | 2025-01-17 | 2025-04-30 | 240208
30024150-EBP | 30024150;2026,AP,Daimler,W520-MF,lamination RL,240207,T,Equipment | 白宇鹏 | 金宇隆 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 缺少质量检查表：——唐红芳 PDL01241792/A-Equipment Process Quality Inspection Form | 2024-11-15 | 2025-01-17 | 2025-04-30 | 240207
30024149-EBP | 30024149;2026,AP,Daimler,W520-MF,lamination FR,240206,T,Equipment | 白宇鹏 | 李华 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 缺少制造资料：——韩冬临 PDL01241624/A-Process Failure Mode & Effects Analysis PDL01241627/A-Equipment & Tooling Assembly Process Form 缺少机械资料：——李华 PDL01241564/A-Special Characteristics List PDL01241608/A-Basic Assessment Ergonomics PDL01241609/A-Drawings/CAD PDL01241610/A-Design Failure Mode & Effects Analysis PDL01241612/A-Equipment Risk/Safety Assessment PDL01241619/A-Delivery Documentation 缺少质量检查表：——唐红芳 PDL01241622/A-Equipment Process Quality Inspection Form | 2024-11-15 | 2025-01-17 | 2025-04-30 | 240206
30024147-EBP | 30024147;2026,AP,Daimler,W520-MF,lamination FL,240205,T,Equipment | 白宇鹏 | 李华 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 缺少制造资料：——韩冬临 PDL01241624/A-Process Failure Mode & Effects Analysis PDL01241627/A-Equipment & Tooling Assembly Process Form 缺少机械资料：——李华 PDL01241564/A-Special Characteristics List PDL01241608/A-Basic Assessment Ergonomics PDL01241609/A-Drawings/CAD PDL01241610/A-Design Failure Mode & Effects Analysis PDL01241612/A-Equipment Risk/Safety Assessment PDL01241619/A-Delivery Documentation 缺少质量检查表：——唐红芳 PDL01241622/A-Equipment Process Quality Inspection Form | 2024-11-15 | 2025-01-17 | 2025-04-30 | 240205
30024143-EBP | 30024143;2026,AP,M Auto,MX11-IP,Spary,240223,4T,Equipment | 夏阳 | 周理文 | Phase Out |  |  | B | B | R |  | G | / | 2024-12-13 | 2025-02-28 | 2025-12-31 | 240223
30024142-EBP | 30024142-2026,AP,M Auto,MX11-IP,Spart,240222,1M,Equipment | 夏阳 | 程德宝 | Phase Out |  |  | B | B | B |  | B | / | 2025-01-17 | 2025-01-24 | 2025-02-28 | 240222
30024136-EBP | 30024136;2026,AP,Mercedes-Benz,V540-IP,Lami,240241,T,Equipment | 夏阳 | 阚城奔 | Phase Out |  |  | B | B | R |  | R | 缺少机械资料：——阚城奔 PDL01240472/A-Special Characteristics List PDL01240488/A-Basic Assessment Ergonomics PDL01240489/A-Drawings/CAD PDL01240499/A-Delivery Documentation SSO自评没有完成——阚城奔 | 2024-12-13 | 2025-01-24 | 2025-12-31 | 240241
30024111-EBP | 30024111;2026,AP,Mercedes-Benz,V540-IP,Lami,240240,1M,Equipment | 夏阳 | 黄琳健 | Phase Out |  |  | B | B | R |  | R | / | 2024-12-13 | 2025-01-15 | 2025-12-31 | 240240
30024110-EBP | 30024110-2026,AP,Mercedes-Benz,V540-IP,Welding,240238,T,Equipment | 夏阳 | 刘璟华 | Phase Out |  |  | B | B | R |  | G | 无重大安全问题 发运前安全分97.14% | 2024-12-13 | 2025-02-14 | 2026-03-31 | 240238
30024097-EBP | 30024097-2026,AP,Mercedes-Benz,V540-IP,Welding,240237,T,Equipment | 夏阳 | 刘璟华 | Phase Out |  |  | B | B | G |  | R | 安全DS自查表没有完成——邱永旭 | 2025-04-30 | 2025-05-31 | 2026-05-31 | 240237
30024096-EBP | 30024096-2026,AP,Mercedes-Benz,V540-IP,Welding,240236,T,Equipment | 夏阳 | 刘璟华 | Phase Out |  | 换模车和把手存在夹点，需要扩大把手空间 | B | B | R |  | G | / | 2024-12-13 | 2025-02-28 | 2026-03-31 | 240236
30024067-EBP | 30024067-2025,AP,SERES Motors,F3-CNSL,lamination，240244，M,Equipment | 陈佳荣 | 黄琳健 | Post Launch |  |  | B | B | B |  | R | 完成 | 2024-10-20 | 2024-10-31 | 2025-02-16 | 240244
30024052-EBP | 30024052-2026,AP,Mercedes-Benz,V540-IP,Welding,240235,Equipment | 夏阳 | 郝秀霞 | Phase Out |  |  | B | B | R |  | G | 无重大安全问题 发运前安全分91.46% | 2025-01-08 | 2025-02-28 | 2026-02-28 | 240235
30024039-EBP | 30024039;2025,AP,BYD,SA6,Flaming，240242，M,Equipment | 尚兵 | 朱聪 | Phase 5 Production Delivery |  |  | B | B | B |  | B | 完成 | 2024-10-16 | 2024-10-23 | 2024-12-16 | 240242
30024016-EBP | 30024016-2024,AP,Geely,L946-AP,Noice,240234,T1,Equipment | 李忆陵 | 韦少官 | Phase Out |  | 线束插拔操作深度超过人机工程尺寸，需要经过客户确认。 | B | B | B |  | B | 完成 | 2024-10-14 | 2024-10-30 | 2025-05-31 | 240234
30023957-EBP | 30023957-2025,AP,BMW,NCAR-IP, WELDING, 240229, T,Equipment | 杨阳 | 刘璟华 | Phase Out |  |  | B | B | R |  | R | 无重大安全问题 发运前安全分95.12% | 2024-11-08 | 2025-11-30 | 2025-02-28 | 240229
30023952-EBP | 30023952;2025,NA,General Motors,L234-IP RHD,punch,240224,T,Equipment | 王保卫 | 韦少官 | Phase Out |  |  | B | B | B |  | B | 完成 | 2024-11-30 | 2024-12-31 | 2025-06-30 | 240224
30023951-EBP | 30023951;2025,NA,General Motors,L234-IP RHD,bonding,240233,T,Equipment | 王保卫 | 周理文 | Phase 5 Production Delivery |  |  | B | B | B |  | B | 完成 | 2024-11-18 | 2024-12-10 | 2025-03-10 | 240233
30023950-EBP | 30023950;2025,NA,General Motors,L234-IP RHD,bonding,240232,T,Equipment | 王保卫 | 周理文 | Phase 5 Production Delivery |  |  | B | B | B |  | B | 完成 | 2024-11-18 | 2024-12-10 | 2025-03-10 | 240232
30023949-EBP | 30023949-2025,NA,General Motors,L234-IP RHD,pre-fix,240231,T,Equipment | 王保卫 | 黄琳健 | Phase 5 Production Delivery |  |  | B | B | B |  | R | / | 2024-11-18 | 2024-12-10 | 2025-03-10 | 240231
30023948-EBP | 30023948-2025,NA,General Motors,L234-IP RHD,pre-fix,240230,T,Equipment | 王保卫 | 黄琳健 | Phase 5 Production Delivery |  |  | B | B | B |  | R | / | 2024-11-18 | 2024-12-10 | 2025-03-30 | 240230
30023947-EBP | 30023947;2025,NA,General Motors,L234-IP RHD,welding,240225,T,Equipment | 王保卫 | 邱永旭 | Phase Out |  |  | B | B | B |  | B | 完成 | 2024-10-18 | 2024-10-25 | 2025-03-10 | 240225
30023946-EBP | 30023946;2025,NA,General Motors,L234-IP RHD,lamination,240227,T,Equipment | 王保卫 | 阚城奔 | Phase 5 Production Delivery |  |  | B | B | B | 遗留 | R | / | 2024-11-08 | 2024-11-21 | 2025-03-31 | 240227
30023934-EBP | 30023934-2025,EMEA,Tes,Tesla Opal-CNSL,Lam,240034,T,Equipment | 郭正阳 | 闵宏恩 | Post Launch |  |  | R | R | R |  |  | phase2：缺少电气资料：徐义星 phase3：缺少电气资料：徐义星 | 2025-07-31 | 2025-08-30 | 2025-12-30 | 240034
30023933-EBP | 30023933;2025,EMEA,Tes,Tesla Opal-CNSL,Lam,240032,M,Equipment | 郭正阳 | 陈洁 | Phase Out |  |  | B | B | B | / | B | / | 2024-11-30 | 2025-05-01 | 2025-05-15 | 240032
30023927-EBP | 30023927;2025,EMEA,Tes,Tesla Opal-CNSL,Lam,240031,M,,Equipment | 郭正阳 | 陈洁 | Phase Out |  |  | B | B | R | / | R | 缺少制造资料：何琳霖 缺少质量检查表：高宇辰 | 2024-11-30 | 2024-12-31 | 2025-06-30 | 240031
30023525-EBP | 30023525;2026,NA,VW Group,VW426-IP,Assembling,240199,M,Equipment | 王翔 | 黄圣 | Phase 5 Production Delivery |  | feeder3和围栏拼接位置缝隙大小没有验证，项目经理反馈只能现场确认。 | B | B | B | / | B | / | 2024-09-27 | 2024-11-22 | 2025-05-19 | 240199
30023478-EBP | 30023478;2026,AP,Brilliance-BMW,G78-HUD, lamination, 240195, T,Equipment | 袁帅 | 周华盛 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2024-09-13 | 2024-12-06 | 2025-04-25 | 240195
30023465-EBP | 30023465;2026,AP,Brilliance-BMW,G78-HUD, lamination, 240194, M,Equipment | 袁帅 | 陈洁 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2024-09-16 | 2024-10-16 | 2025-04-25 | 240194
30023422-EBP | 30023422-2026,AP,Mercedes-Benz,V540-DP,Lami,240187,1T,Equipment | 夏阳 | 闵宏恩 | Phase 5 Production Delivery |  |  | B | R | R |  | R | 缺少电气资料：——范如松/夏阳 PDL01280220/A-Control Logic Diagram of Safety System PDL01280238/A-Safety Functions Evaluation of Machine PDL01280205/A-Equipment Safety Design Checklist (Electrical) | 2025-02-28 | 2025-04-30 | 2026-03-31 | 240187
30023421-EBP | 30023421;2026,AP,Mercedes-Benz,V540-DP,Lami,240186,1T,Equipment | 夏阳 | 闵宏恩 | Phase 4 Manufacturing Development |  |  | B | R | R |  | R | 无重大安全问题 发运前安全分87.1% | 2025-02-28 | 2025-04-30 | 2025-12-31 | 240186
30023418-EBP | 30023418;2026,AP,Mercedes-Benz,V540-DP,Lami,240185,1T,Equipment | 夏阳 | 高一恒 | Phase 4 Manufacturing Development |  | / | B | B | R | / | R | / | 2024-12-13 | 2025-02-28 | 2025-12-31 | 240185
30023416-EBP | 30023416;2026,AP,Mercedes-Benz,V540-DP,Lami,240184,1T,Equipment | 夏阳 | 高一恒 | Phase 4 Manufacturing Development |  | / | B | B | R | / | R | 未指派任务% | 2024-11-30 | 2025-02-28 | 2025-12-31 | 240184
30023413-EBP | 30023413-2025,AP,smartmi,MX11-DAB，Lamination, 240160, M,Equipment | 邹成成 | 陈洁 | Post Launch |  | / | B | B | R | / | R | PDL01217368/A-Equipment Safety Status Checkilst PDL01217377/A-Equipment Process Quality Inspection Form | 2024-09-22 | 2024-12-15 | 2025-06-15 | 240160
30023381-EBP | 30023381;2025,AP,SERES Motors,F3-DP,lamination，240192,M,Equipment | 陈佳荣 | 陈斌 | Post Launch |  | / | B | B | B | / | R | 完成 | 2024-09-06 | 2024-09-21 | 2024-11-30 | 240192
30023368-EBP | 30023368;2026,AP,Mercedes-Benz,V540-DP,Lami,240183,1M,Equipment | 夏阳 | 陈洁 | Phase 4 Manufacturing Development |  | / | B | B | R | / | R | 无重大安全问题 发运前安全分74,42% | 2024-12-13 | 2025-02-28 | 2025-12-31 | 240183
30023367-EBP | 30023367;2026,AP,Mercedes-Benz,V540-IP,Injection-auto,240188,1M,Equipment | 夏阳 | 程德宝 | Phase 4 Manufacturing Development |  | / | B | B | R | / | R | / | 2024-12-31 | 2025-02-28 | 2025-12-31 | 240188
30022845-EBP | 30022845;2025,AP,SERES Motors,F3-IP.Vacuum,240182,M,Equipment | 孟子冰 | 陈洁 | Post Launch |  | 如换模位平台突出部分下方没有斜支撑（平台强度需要模拟或计算），二三层的爬梯未分开，无自回复门，围栏与爬梯间的缝隙过大等等（参考GB/T 17888.1-4） 取放件工位水平光栅存在盲区，竖直光栅高度低于1600mm 取放件工位两侧矮围栏高度太低，中间矮围栏与转台间存在过大间隙 二层平台的（两个）升降压合机构应该设计维修安全柱 后侧平台光栅的复位按钮安装位置 | B | B | B | / | R | 完成 | 2024-09-14 | 2024-09-17 | 2024-12-12 | 240182
30022712-EBP | 30022712;2025,AP,smartmi,MX11,Fixing,240181,T,Equipment | 尚兵 | 陈斌 | Phase Out |  | / | B | B | B | 遗留 | R | 完成 | 2024-08-28 | 2024-09-06 | 2024-10-31 | 240181
30022681-EBP | 30022681-2025,AP,Daimler,BR 223-DP,Welding,240180,T,Equipment | 赵军 | 王小龙 | Phase0 |  | / | B | B | B | / | B | 完成 | 2024-09-15 | 2024-10-16 | 2024-12-20 | 240180
30022667-EBP | 30022667;2025,AP,SERES Motors,F3-CNSL,Lamination,240178,M,Equipment | 陈佳荣 | 陈子翌 | Post Launch |  | / | B | B | B | / | R | 完成 | 2024-09-01 | 2024-10-18 | 2025-02-16 | 240178
30022666-EBP | 30022666;2025,AP,SERES Motors,F3-CNSL,lamination,240179,M,Equipment | 陈佳荣 | 赵书泰 | Post Launch |  | / | B | B | B | / | R | 完成 | 2024-08-31 | 2024-10-18 | 2025-02-16 | 240179
30022663-EBP | 30022663;2025,AP,M Auto,MX11,Flaming1,240134,M,Equipment | 尚兵 | 朱聪 | Phase 5 Production Delivery |  | / | B | B | B | / | / | / | 2024-08-16 | 2024-08-23 | 2024-09-06 | 240134
30022592-EBP | 30022592;2024,AP,Agrale,ASC Hot stake,240173,1M,Equipment | 李忆陵 | 刘璟华 | Post Launch |  | 研发项目 | B | B | B | 研发项目 | / | 研发项目 | 2024-08-05 | 2024-08-20 | 2024-09-10 | 240173
30022560-EBP | 30022560;2025,AP,M Auto,MX11-IP,Spart,240158,M,Equipment | 夏阳 | 程德宝 | Phase 5 Production Delivery |  |  | B | B | R |  | R | 无重大安全问题 发运前安全分70.77% | 2025-02-14 | 2025-03-07 | 2025-11-28 | 240158
30022450-EBP | 30022450;2026,AP,SVW,VW426-PAB Chute Punch,240167,M,Equipment | 龚胜超 | 韦少官 | Phase Out |  | / | B | B | B | / | R | / | 2024-08-09 | 2024-08-30 | 2024-11-15 | 240167
30022447-EBP | 30022447;2026,AP,SVW,VW426 PAB Auto Cell,240164, M,Equipment | 龚胜超 | 黄定辉 | Post Launch |  | / | B | B | B | / | B | DONE | 2024-08-24 | 2024-10-11 | 2025-01-10 | 240164
30022345-EBP | 30022345;2025,AP,smartmi,MX11-DAB,Lamination,240159,T,Equipment | 邹成成 | 阚城奔 | Phase 5 Production Delivery |  | / | B | B | R | / | R | 缺少制造资料——陈帅 缺少质量检查表——高宇辰 | 2025-01-31 | 2025-02-23 | 2025-05-31 | 240159
30022330-EBP | 30022330;2026,AP,VW Group,VW426-DP,Lam,240156,T,Equipment | 龚胜超 | 阚城奔 | Phase Out |  | / | B | B | R | / | R | SSO自评没有完成——阚城奔 | 2024-08-23 | 2024-10-11 | 2025-04-30 | 240156
30022329-EBP | 30022329-2026,AP,VW Group,VW426 DP Upper Lam 240155,T,Equipment | 龚胜超 | 樊爱强 | Phase Out |  | / | B | B | B | / | R | / | 2024-08-23 | 2024-10-11 | 2025-04-30 | 240155
30022299-EBP | 30022299;2025,AP,Volkswagen,VW426-DP,lam&wrap,240151,1T,Equipment | 王保卫 | 金宇隆 | Phase 5 Production Delivery |  | / | B | B | B | / | R | 完成 | 2024-08-08 | 2024-11-30 | 2025-04-30 | 240151
30022298-EBP | 30022298;2025,AP,Volkswagen,VW426-DP,lam&wrap,240150,1T,Equipment | 王保卫 | 金宇隆 | Phase 5 Production Delivery |  | / | B | B | R | / | R | 缺少机械资料：——李华 PDL01179474/A-Design Failure Mode & Effects Analysis PDL01179478/A-Equipment Risk/Safety Assessment PDL01179486/A-Delivery Documentation 自评没有完成——李华 | 2024-08-08 | 2024-11-30 | 2025-04-30 | 240150
30022060-EBP | 30022060;2024,AP,Geely,HX11 IP,Laser-W,240144,1M1T,Equipment | 李忆陵 | 陈志斌 | Post Launch |  | / | B | B | B | / | R | / | 2024-08-13 | 2024-09-13 | 2024-12-13 | 240144
30021964-EBP | 30021964;2025,AP,M Auto,MX11,Flaming,240134,M,Equipment | 尚兵 | 朱聪 | Terminated |  | / | B | B | B | / | / | / | 2024-07-27 | 2024-08-10 | 2024-09-28 | 240134
30021953-EBP | 30021953;2025,NA,Tes,Everest-IP,Lamination,240132,M,Equipment | 王翔 | 陈洁 | Phase Out |  | / | B | B | B | 终止 | R | / | 2024-07-19 | 2024-08-06 | 2024-09-05 | 240132
30021952-EBP | 30021952;2025,NA,Tes,Everest-IP,Lamination,240131,T,Equipment | 王翔 | 陈子翌 | Phase Out |  | / | B | B | B | 终止 | R | / | 2024-07-19 | 2024-08-06 | 2024-09-05 | 240131
30021951-EBP | 30021951;2025,NA,Tes,Everest-IP,pre-fix,240119,T,Equipment | 王翔 | 朱聪 | Phase Out |  | / | B | B | B | 终止 | R | / | 2024-07-19 | 2024-08-06 | 2024-09-05 | 240119
30021950-EBP | 30021950;2025,NA,Tes,Everest-IP,scoring fix,240130,T,Equipment | 王翔 | 王万芳 | Phase Out |  | / | B | B | B | 终止 | R | / | 2024-07-18 | 2024-08-06 | 2024-09-05 | 240130
30021949-EBP | 30021949;2025,NA,Tes,Everest-IP,socring fix,240129,M,Equipment | 王翔 | 黄定辉 | Phase Out |  | / | B | B | B | 终止 | R | / | 2024-07-18 | 2024-08-06 | 2024-09-05 | 240129
30021923-EBP | 30021923;2025,NA,Tes,Everest-IP,Glue,240128,M,Equipment | 王翔 | 程德宝 | Phase Out |  | / | B | B | B | 终止 | R | / | 2024-07-19 | 2024-08-06 | 2024-09-05 | 240128
30021922-EBP | 30021922;2025,NA,Tes,Everest-IP,Glue,240127,T,Equipment | 王翔 | 周理文 | Phase Out |  | / | B | B | B | / | B | 完成 | 2024-07-31 | 2024-11-22 | 2025-03-31 | 240127
30021921-EBP | 30021921;2025,NA,Tes,Everest-IP,Glue,240126,M,Equipment | 王翔 | 程德宝 | Phase Out |  | / | B | B | B | / | B | 完成 | 2024-07-31 | 2024-08-06 | 2025-05-16 | 240126
30021920-EBP | 30021920;2025,NA,Tes,Everest-IP,Flaming,240125,T,Equipment | 王翔 | 邱永旭 | Phase Out |  | / | B | B | B | 终止 | R | / | 2024-07-31 | 2024-08-28 | 2024-09-19 | 240125
30021919-EBP | 30021919;2025,NA,Tes,Everest-IP,Flaming,240124,M,Equipment | 王翔 | 黄圣 | Phase Out |  | / | B | B | B | 终止 | R | / | 2024-07-31 | 2024-08-28 | 2024-09-19 | 240124
30021892-EBP | 30021892-2026,AP,Daimler,W520,IP OP2-R,240090,T,Equipment | 白宇鹏 | 邱永旭 | Post Launch |  | / | B | B | B | / | R | 等待领导审批——郝同森 | 2024-06-29 | 2024-07-31 | 2025-02-10 | 240090
30021891-EBP | 30021891-2026,AP,Daimler,W520,IP OP1-R,240089,T,Equipment | 白宇鹏 | 邱永旭 | Post Launch |  | / | B | B | B | / | R | 等待领导审批——郝同森 | 2024-06-29 | 2024-07-31 | 2025-02-10 | 240089
30021890-EBP | 30021890-2026,AP,Daimler,W520.IP OP2-L.240088.T,Equipment | 白宇鹏 | 邱永旭 | Post Launch |  | / | B | B | B | / | B | / | 2024-06-29 | 2024-07-31 | 2024-12-30 | 240088
30021889-EBP | 30021889-2026,AP,Daimler,W520.IP OP1-L.240087,T,Equipment | 白宇鹏 | 邱永旭 | Post Launch |  | / | B | B | B | / | B | / | 2024-06-29 | 2024-07-31 | 2024-12-30 | 240087
30021888-EBP | 30021888-2026,AP,Daimler,W520,GB,welding,240092,T,Equipment | 白宇鹏 | 刘璟华 | Post Launch |  | / | B | B | B | / | B | / | 2024-07-27 | 2024-08-17 | 2024-12-30 | 240092
30021887-EBP | 30021887-2026,AP,Daimler,W520-CUN,welding,240091,T,Equipment | 白宇鹏 | 邱永旭 | Post Launch |  | / | B | B | B | / | B | / | 2024-07-27 | 2024-08-16 | 2024-12-30 | 240091
30021886-EBP | 30021886-2026,AP,Daimler,W520-CUN,Glue spray,240086,T,Equipment | 白宇鹏 | 陈斌 | Phase0 |  | / | B | B | B | / | R | DONE | 2024-07-27 | 2024-08-17 | 2024-12-30 | 240086
30021883-EBP | 30021883-2026,AP,Daimler,W520-CUN.lamination,240079,T,Equipment | 白宇鹏 | 陈子翌 | Phase0 |  | / | B | B | B | / | R | 完成 | 2024-07-27 | 2024-08-17 | 2024-12-31 | 240079
30021844-EBP | 30021844;2024,NA,Tes,Highland-CNSL,,EOL,240107,T,Equipment | 王翔 | 黄定辉 | Phase Out |  | 终止 | B | B | B | 终止 | R | / | 2024-05-20 | 2024-08-30 | 2024-09-13 | 240107
30021644-EBP | 30021644;2024,AP,smartmi,MS11,Lamination，240102，M,Equipment | 尚兵 | 陈斌 | Phase Out |  | / | B | B | B | / | R | / | 2024-06-29 | 2024-07-12 | 2024-08-09 | 240102
30021618-EBP | 30021618;2024,AP,BAIC,C71KB-IP,Lamination,240097, M,Equipment | 邱伯超 | 黄定辉 | Phase Out |  | / | B | B | B | / | R | / | 2024-06-08 | 2024-06-18 | 2024-08-30 | 240097
30021425-EBP | 30021425-2024,AP,Li Auto,W03-DAB,Lamination,240081,M,Equipment | 袁帅 | 陈洁 | Terminated |  | / | B | B | R | / | G | 无重大安全问题 93.33% | 2024-05-31 | 2024-06-07 | 2025-12-26 | 240081
30021325-EBP | 30021325-2025,AP,Huawei Anhui,C71KB-IP,Lamination,240078,M,Equipment | 尚兵 | 陈斌 | Post Launch |  | / | B | B | B | / | B | 完成 | 2024-06-15 | 2024-06-28 | 2024-12-30 | 240078
30021237-EBP | 30021237-2024,AP,Brilliance-BMW,Ncar NA6-IP,Lamination,240076,T,Equipment | 孟子冰 | 黄东方 | Phase 5 Production Delivery |  | / | B | B | B | / | R | 完成 | 2024-06-28 | 2024-07-28 | 2024-11-16 | 240076
30021236-EBP | 30021236-2024,AP,Brilliance-BMW,Ncar NA6-IP,Lamination,240075,T,Equipment | 孟子冰 | 黄东方 | Phase 5 Production Delivery |  | B | B | B | B | 遗留 | R | / | 2024-06-28 | 2024-07-28 | 2024-11-16 | 240075
30021232-EBP | 30021232-2024,AP,Brilliance-BMW,Ncar NA6-IP,Welding,240076,M,Equipment | 孟子冰 | 黄东方 | Terminated |  | / | B | B | B | 终止 | / | 项目取消 | 2024-07-08 | 2024-07-03 | 2024-10-25 | 240076
30021200-EBP | 30021200;2024,AP,Volkswagen,AS33-IP,Flame,240074,M,Equipment | 尚兵 | 朱聪 | Phase Out |  | / | B | B | B | / | R | / | 2024-05-31 | 2024-06-08 | 2024-08-31 | 240074
30020977-EBP | 30020977-2026,AP,Volkswagen,VW426-DP,welding,240072,16T,Equipment | 王保卫 | 刘璟华 | Phase 5 Production Delivery |  | / | B | B | R | / | R | 缺少制造资料：——潘翼伟 PDL01236907/A-Process Failure Mode & Effects Analysis SSO自评没有完成——高大尉 | 2024-05-16 | 2024-06-15 | 2025-05-31 | 240072
30020975-EBP | 30020975;2026,AP,VW Group,VW426-DP, welding, 240071, 2M,Equipment | 王保卫 | 郝秀霞 | Phase 4 Manufacturing Development |  | / | B | B | R | / | R | 缺少制造资料：——潘翼伟 PDL01236910/A-Equipment & Tooling Assembly Process Form SSO自评没有完成——郝秀霞 | 2024-06-30 | 2024-08-05 | 2025-12-31 | 240071
30020950-EBP | 30020950;2024,AP,BMW,G60-Armrest,lamination,240070,T,Equipment | 樊皆杰 | 樊爱强 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2024-05-09 | 2024-05-17 | 2024-08-17 | 240070
30020949-EBP | 30020949;2024,AP,BMW,G60-Armrest,lamination.240069,T,Equipment | 樊皆杰 | 樊爱强 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2024-05-09 | 2024-05-17 | 2024-08-17 | 240069
30020867-EBP | 30020867-2024,AP,Tes,Rivian-DP,lamination,240063,T,Equipment | 曹春 | 韦少官 | Phase Out |  | / | B | B | B | / | B | / | 2024-06-07 | 2024-06-14 | 2024-12-13 | 240063
30020866-EBP | 30020866-2024,AP,Tes,Rivian-DP,lamination,240062,T,Equipment | 曹春 | 韦少官 | Phase Out |  | / | B | B | B | / | B | / | 2024-06-07 | 2024-06-14 | 2024-12-10 | 240062
30020865-EBP | 30020865-2024,AP,Tes,Rivian-DP,toolpack,240061,T,Equipment | 曹春 | 韦少官 | Phase Out |  | / | B | B | B | / | B | / | 2024-06-07 | 2024-06-14 | 2024-12-13 | 240061
30020585-EBP | 30020585;2025,AP,Others,2050IRadd,renovation,240041,M,Equipment | 张智浩 |  | Cancel/Pending |  | / | B | B | B | / | / | / | 2024-02-13 | 2024-04-01 | 2024-04-10 | 240041
30020439-EBP | 30020439;2025,AP,smartmi,MX11-IP,Lamination,240035,M,Equipment | 尚兵 | 陈斌 | Phase 5 Production Delivery |  | / | B | B | B | / | B | / | 2024-05-25 | 2024-06-28 | 2024-09-14 | 240035
30020438-EBP | 30020438;2025,AP,smartmi,MX11-IP,Lamination,240036,T,Equipment | 尚兵 | 赵书泰 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2024-05-26 | 2024-06-26 | 2024-08-10 | 240036
30020435-EBP | 30020435;2025,EMEA,Daimler,X244-IP,Welding,240029,T,Equipment | 郭正阳 | 高大尉 | Phase Out |  | / | B | B | B | / | B | 完成 | 2024-06-18 | 2024-10-12 | 2024-11-18 | 240029
30020434-EBP | 30020434;2025,EMEA,Tes,Tesla Opal,Console,Lam,240034,T,Equipment | 郭正阳 | 闵宏恩 | Post Launch |  | / | B | B | B | / | R | DONE | 2024-07-28 | 2024-08-28 | 2024-12-31 | 240034
30020433-EBP | 30020433;2025,EMEA,Tes,Tesla Opal,Console,Lam,240032,M,Equipment | 郭正阳 | 陈洁 | Cancel/Pending |  | / | B | B | B | / | / | DONE | 2024-07-28 | 2024-08-28 | 2024-12-31 | 240032
30020432-EBP | 30020432;2025,EMEA,Tes,Tesla Opal-Console,Lam,240031,M,Equipment | 郭正阳 | 陈洁 | Cancel/Pending |  | / | B | B | B | / | / | DONE | 2024-07-29 | 2024-08-29 | 2024-12-31 | 240031
30020431-EBP | 30020431;2025,EMEA,Tes,Tesla Opal-Console,Lam,240033,M,Equipment | 郭正阳 | 陈洁 | Post Launch |  | / | B | B | B | / | R | 项目撤销 | 2024-07-28 | 2024-08-28 | 2024-12-31 | 240033
30019756-EBP | 30019756;2026,AP,Brilliance-BMW,NCAR-DP,Lamination,240025,M,DP,Equipment | 尚兵 | 陈斌 | Phase 5 Production Delivery |  | 取放件两侧缺少禁止踩踏和禁止通行标签。光栅缺少独立复位按钮，项目经理反馈已通过客户确认。 | B | B | B | / | R | 完成 | 2024-07-19 | 2024-08-30 | 2024-10-30 | 240025
30019755-EBP | 30019755;2026,AP,Brilliance-BMW,NCAR-DP,Lamination,240024,M,DP,Equipment | 尚兵 | 陈斌 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2024-03-30 | 2024-05-10 | 2024-05-24 | 240024
30019510-EBP | 30019510;2024,AP,BMW,G4X-INT,EOL,240018,M,Equipment | 陈佳荣 | 程德宝 | Post Launch |  | / | B | B | B | / | R | / | 2024-03-30 | 2024-04-30 | 2024-05-31 | 240018
30019509-EBP | 30019509;2024,AP,BMW,G3X-INT,EOL,240020,Equipment | 陈佳荣 | 陈志斌 | Post Launch |  | / | B | B | B | / | / | / | 2024-03-30 | 2024-04-30 | 2024-05-31 | 240020
30019508-EBP | 30019508;2024,AP,BMW,G4X-INT,EOL,240021,M,Equipment | 陈佳荣 | 杜全喆 | Post Launch |  | / | B | B | B | / | / | / | 2024-03-30 | 2024-04-30 | 2024-05-31 | 240021
30019507-EBP | 30019507-2024,AP,BMW,G4X-INT,EOL,240022,M,Equipment | 陈佳荣 | 冯全华 | Post Launch |  | / | B | B | B | / | R | / | 2024-03-30 | 2024-04-30 | 2024-05-31 | 240022
30019455-EBP | 30019455-2025,AP,Li Auto,W03DAB,lamination,240016,T,Equipment | 袁帅 | 陈子翌 | Terminated |  | / | B | B | R | / | R | 无重大安全问题 93% | 2024-03-15 | 2024-05-15 | 2025-12-26 | 240016
30019425-EBP | 30019425-2025,NA,Ford,U759-DP,welding,230076,T,Equipment | 王翔 | 高大尉 | Phase Out |  | / | G | G | G | / | / | / | 2026-06-08 | 2026-09-16 | 2027-05-18 | 230076
30019409-EBP | 30019409;2024,AP,BMW,G4X-DP,EOL,240014.M,Equipment | 陈佳荣 | 程德宝 | Post Launch |  | / | B | B | B | 终止 | R | / | 2024-08-01 | 2024-09-01 | 2024-11-01 | 240014
30019076-EBP | 30019076;2025,AP,Others,lamination,240008,M,Equipment | 樊皆杰 | 陈洁 | Cancel/Pending |  | / | B | B | B | / | / | / | 2024-03-16 | 2024-04-09 | 2024-05-09 | 240008
30019075-EBP | 30019075;2025,AP,Others,lamination,240007,M,Equipment | 樊皆杰 | 陈洁 | Cancel/Pending |  | / | B | B | B | / | / | / | 2024-03-16 | 2024-04-09 | 2024-05-09 | 240007
30018924-EBP | 30018924-2024,AP,BMW,G45-DP,lamination, 240001,1M,Equipment | 曹春 | 陈洁 | Post Launch |  | / | B | B | B | / | B | 完成 | 2024-04-09 | 2024-04-19 | 2024-08-16 | 240001
30018552-EBP | 30018552;2025,NA,Ford,U759-DP,welding,230075,M,Equipment | 王翔 | 郝秀霞 | Phase Out |  | / | R | G | G | / | R | / | 2023-12-19 | 2026-09-16 | 2027-05-18 | 230075
30018551-EBP | 30018551;2024,AP,BYD,HA5-DP,lamination,230282,T,Equipment | 陈佳荣 | 闵宏恩 | Phase Out |  | / | B | B | B | / | B | 完成 | 2023-12-27 | 2024-01-10 | 2024-10-31 | 230282
30018487-EBP | 30018487;2024,NA,Rivian,Premium-DP,Lamination,230292,T,Equipment | 王翔 | 陈子翌 | Phase Out |  | / | B | B | B | / | R | / | 2023-11-27 | 2024-01-10 | 2024-04-05 | 230292
30018486-EBP | 30018486;2024,NA,Rivian,Premium-DP,Lamination,230291,T,Equipment | 王翔 | 陈子翌 | Phase Out |  | / | B | B | B | / | R | / | 2023-11-27 | 2024-01-10 | 2024-04-05 | 230291
30018485-EBP | 30018485;2024,NA,Rivian,Premium-DP,Lamination,230290,T,Equipment | 王翔 | 陈子翌 | Phase Out |  | / | B | B | B | / | R | / | 2023-11-27 | 2024-01-10 | 2024-04-05 | 230290
30018484-EBP | 30018484;2024,NA,Rivian,Premium-DP,Lamination,230289,T,Equipment | 王翔 | 陈子翌 | Phase Out |  | / | B | B | B | / | R | / | 2023-11-27 | 2024-01-10 | 2024-04-05 | 230289
30018483-EBP | 30018483;2024,NA,Rivian,Premium-DP,Lamination,230288,T,Equipment | 王翔 | 陈子翌 | Phase Out |  | / | B | B | B | / | R | / | 2023-11-27 | 2024-01-10 | 2024-04-05 | 230288
30018482-EBP | 30018482;2024,NA,Rivian,Premium-DP,Lamination,230287,T,Equipment | 王翔 | 陈子翌 | Phase Out |  | / | B | B | B | / | R | / | 2023-11-27 | 2024-01-10 | 2024-04-05 | 230287
30018481-EBP | 30018481;2024,NA,Rivian,Premium-DP,Lamination,230286,M,Equipment | 王翔 | 陈洁 | Phase Out |  | / | B | B | B | / | R | / | 2023-11-16 | 2023-11-22 | 2024-02-26 | 230286
30018116-EBP | 30018116;2014,AP,Brilliance-BMW,G4X-Lbar,assembly,230280,M,Equipment | 陈佳荣 | 程德宝 | Phase Out |  | / | B | B | B | / | R | / | 2024-01-25 | 2024-03-20 | 2024-04-30 | 230280
30018109-EBP | 30018109;2024,AP,Tes,Q36-DAB,Lamination,230275,T,Equipment | 邹成成 | 周华盛 | Post Launch |  | / | B | B | B | / | R | / | 2024-03-08 | 2024-03-15 | 2024-06-14 | 230275
30018108-EBP | 30018108;2024,EMEA,Tes,Q36-DAB,Lamination,230276,M,Equipment | 邹成成 | 陈斌 | Post Launch |  | / | B | B | B | / | R | / | 2024-03-08 | 2024-03-15 | 2024-06-14 | 230276
30018107-EBP | 30018107;2024,AP,Tes,Q36-DAB,Lamination,230277,M,Equipment | 邹成成 | 陈斌 | Post Launch |  | / | B | B | B | / | R | / | 2024-03-08 | 2024-03-15 | 2024-06-14 | 230277
30018019-EBP | 30018019;2024,AP,BYD,MRHB-CNSL,lamination,230265,T,Equipment | 陈佳荣 | 闵宏恩 | Phase Out |  | / | B | B | B | / | R | / | 2023-11-15 | 2023-12-20 | 2024-06-30 | 230265
30017999-EBP | 30017999;2024,AP,BYD,MRHB-IP,lamination，230270，T,Equipment | 陈佳荣 | 闵宏恩 | Phase Out |  | / | B | B | B | / | R | / | 2023-11-14 | 2023-12-20 | 2024-01-30 | 230270
30017998-EBP | 30017998;2024,AP,BYD,MRHB-IP,lamination，230269，T,Equipment | 陈佳荣 | 闵宏恩 | Phase Out |  | / | B | B | B | / | R | / | 2023-11-15 | 2023-12-20 | 2024-01-30 | 230269
30017997-EBP | 30017997;2024,AP,BYD,MRHB-IP,lamination，230268,T,Equipment | 陈佳荣 | 闵宏恩 | Phase Out |  | / | B | B | B | / | R | / | 2023-11-14 | 2023-12-20 | 2024-01-30 | 230268
30017996-EBP | 30017996;2024,AP,BYD,MRHB-IP,lamination，230267，T,Equipment | 陈佳荣 | 闵宏恩 | Phase Out |  | / | B | B | B | / | R | / | 2023-11-14 | 2023-12-20 | 2024-01-30 | 230267
30017983-EBP | 30017983;2024,AP,Audi FAW NEV,AU403-IP,Welding,230255,T,Equipment | 夏阳 | 周理文 | Phase Out |  | / | B | B | B | / | R | / | 2024-01-15 | 2024-03-15 | 2024-05-31 | 230255
30017982-EBP | 30017982;2024,AP,Geely-Volvo,723K-IP,Welding,230263,4T,Equipment | 袁帅 | 周理文 | Phase Out |  | / | B | B | B | / | R | / | 2024-01-02 | 2024-01-31 | 2024-03-01 | 230263
30017858-EBP | 30017858;2024,AP,Tes,Bezier-DP,lamination,230257,1T,Equipment | 王保卫 | 王万芳 | Phase Out |  | / | B | B | B | / | R | / | 2023-10-30 | 2024-04-15 | 2024-09-30 | 230257
30017837-EBP | 30017837;2024,AP,Geely,E371-DP,lamination,230238,Equipment | 夏阳 | 黄东方 | Post Launch |  | / | B | B | B | / | R | / | 2024-01-01 | 2024-02-01 | 2024-03-02 | 230238
30017647-EBP | 30017647;2023,AP,Tes,everest-IP,lamination,230131,m,Equipment | 王翔 | 陈洁 | Phase Out |  | / | B | B | B | / | R | / | 2023-10-07 | 2023-11-07 | 2023-12-07 | 230131
30017619-EBP | 30017619;2024,AP,Tes,Q36-DAB,Lamination,230254,M,Equipment | 邹成成 | 陈斌 | Post Launch |  | / | B | B | B | / | R | / | 2024-03-08 | 2024-03-15 | 2024-06-14 | 230254
30017544-EBP | 30017544-2023,AP,VW Group,VW416_DP,lamination,230151,T,Equipment | 曹春 | 樊爱强 | Phase Out |  | / | B | B | B | / | R | / | 2023-09-08 | 2023-11-01 | 2023-12-12 | 230151
30017543-EBP | 30017543;2023,AP,VW Group,VW416_DP,lamination,230150,T,Equipment | 曹春 | 樊爱强 | Phase Out |  | / | B | B | R | / | R | / | 2023-09-08 | 2023-11-01 | 2023-12-15 | 230150
30017542-EBP | 30017542;2023,AP,VW Group,VW416_DP,lamination,230149,T,Equipment | 曹春 | 樊爱强 | Phase Out |  | / | B | B | B | / | R | / | 2023-08-21 | 2023-11-03 | 2023-12-15 | 230149
30017541-EBP | 30017541;2023,AP,Toyota,780B_DP,lamination,230148,T,Equipment | 曹春 | 樊爱强 | Phase Out |  | / | B | B | B | / | R | / | 2023-08-21 | 2023-09-27 | 2023-10-30 | 230148
30017540-EBP | 30017540;2023,AP,Toyota,780B_DP,Lamination,230147,T,Equipment | 曹春 | 樊爱强 | Phase Out |  | / | B | B | B | / | R | / | 2023-08-21 | 2023-09-25 | 2023-10-30 | 230147
30017539-EBP | 30017539;2023,AP,Toyota,780B_DP, Lamination,230145,T,Equipment | 曹春 | 樊爱强 | Phase Out |  | / | B | B | B | / | R | / | 2023-08-21 | 2023-09-19 | 2023-11-22 | 230145
30017535-EBP | 30017535;2024,AP,Tes,Q36-DAB,Lamination,230253,T,Equipment | 邹成成 | 周华盛 | Post Launch |  | / | B | B | B | / | R | / | 2023-10-13 | 2023-10-17 | 2023-10-26 | 230253
30017500-EBP | 30017500;2025,AP,BMW,NA5-IP RHD,Lamination,230247,T,Equipment | 杨阳 | 周华盛 | Phase Out |  | / | B | B | B | / | R | / | 2023-12-15 | 2024-01-31 | 2025-05-31 | 230247
30017475-EBP | 30017475;2024,NA,Tes,Everest-IP,Lamination,230134,T,Equipment | 王翔 | 黄东方 | Phase Out |  | / | B | B | B | / | R | / | 2023-07-12 | 2023-08-11 | 2023-10-18 | 230134
30017474-EBP | 30017474;2024,NA,Tes,Everest-IP,Lamination,230133,T,Equipment | 王翔 | 黄东方 | Phase Out |  | / | B | B | B | / | R | / | 2023-07-12 | 2023-08-11 | 2023-10-18 | 230133
30017473-EBP | 30017473;2024,NA,Tes,Everest-IP,Lamination,230132,T,Equipment | 王翔 | 黄东方 | Phase Out |  | / | B | B | B | / | R | / | 2023-07-12 | 2023-08-11 | 2023-10-18 | 230132
30017455-EBP | 30017455;2025,AP,Audi FAW NEV,AU511-DP,lamination，230239，T,Equipment | 陈佳荣 | 周华盛 | Phase Out |  | / | B | B | B | / | / | 完成 | 2023-10-20 | 2024-11-18 | 2024-12-07 | 230239
30017454-EBP | 30017454;2025,AP,Audi FAW NEV,AU511-DP,lamination，230244，T,Equipment | 陈佳荣 | 周华盛 | Phase Out |  | / | B | B | B | / | R | / | 2023-10-20 | 2023-11-05 | 2024-01-25 | 230244
30017453-EBP | 30017453;2025,AP,Audi FAW NEV,AU511-DP,lamination，230245，T,Equipment | 陈佳荣 | 周华盛 | Phase Out |  | / | B | B | B | / | R | / | 2023-10-20 | 2023-11-05 | 2024-01-25 | 230245
30017452-EBP | 30017452;2025,AP,Audi FAW NEV,AU511-DP,laminaiton，230246，T,Equipment | 陈佳荣 | 周华盛 | Phase Out |  | / | B | B | B | / | R | / | 2023-10-20 | 2023-11-05 | 2024-01-25 | 230246
30017451-EBP | 30017451-2025,AP,Daimler,BR223-DP,Glue Spray,230195,T,Equipment | 赵军 | 陈志斌 | Post Launch |  | / | B | B | B | / | B | / | 2024-01-16 | 2024-02-20 | 2024-09-20 | 230195
30017450-EBP | 30017450-2025,AP,Daimler,BR223-DP,Glue Spray,230194,T,Equipment | 赵军 | 陈志斌 | Post Launch |  | / | B | B | B | / | B | / | 2024-01-19 | 2024-02-23 | 2024-09-20 | 230194
30017400-EBP | 30017400-2025,AP,Daimler,BR223-DP,Glue Spray,230236,M,Equipment | 赵军 | 陈志斌 | Post Launch |  | / | B | B | B | / | R | / | 2023-12-29 | 2024-01-19 | 2024-07-31 | 230236
30017379-EBP | 30017379;2024,NA,Tes,Everest-IP,Wrapping,230167,T,Equipment | 王翔 | 陈子翌 | Phase Out |  | / | B | B | B | / | R | / | 2023-07-12 | 2023-08-11 | 2023-10-18 | 230167
30017378-EBP | 30017378;2024,NA,Tes,Everest-IP,Wrapping,230166,T,Equipment | 王翔 | 陈子翌 | Phase Out |  | / | B | B | B | / | R | / | 2023-07-12 | 2023-08-11 | 2023-10-18 | 230166
30017377-EBP | 30017377;2024,NA,Tes,Everest-IP,Wrapping,230165,T,Equipment | 王翔 | 陈子翌 | Phase Out |  | / | B | B | B | / | R | / | 2023-07-12 | 2023-08-11 | 2023-10-18 | 230165
30017344-EBP | 30017344-2025,AP,Daimler,BR223-DP,Glue Spray,230193,T,Equipment | 赵军 | 陈志斌 | Post Launch |  | / | B | B | B | / | R | / | 2023-12-29 | 2024-01-19 | 2024-08-09 | 230193
30017338-EBP | 30017338;2024,AP,BAIC,C71KB-Ambient,Milling,230208,M,Equipment | 孟子冰 |  | Phase Out |  | / | B | B | B | / | R | / | 2024-02-29 | 2024-05-31 | 2024-06-28 | 230208
30017327-EBP | 30017327;2024,AP,Brilliance-BMW,G48-SEAT,Lamination,230024,M,Equipment | 陈佳荣 | 陈洁 | Post Launch |  | / | B | B | B | / | R | / | 2023-02-16 | 2023-03-16 | 2023-11-30 | 230024
30017313-EBP | 30017313-2025,AP,Daimler,BR223-DP,Welding,230230,T,Equipment | 赵军 | 王小龙 | Phase0 |  | / | B | B | B | / | R | / | 2023-11-17 | 2024-02-01 | 2024-05-30 | 230230
30017312-EBP | 30017312-2025,AP,Daimler,BR223-DP,Welding,230229,M,Equipment | 赵军 | 王小龙 | Phase0 |  | / | B | B | B | / | R | / | 2023-11-21 | 2024-02-01 | 2024-07-12 | 230229
30017311-EBP | 30017311;2024,AP,Brilliance-BMW,G48-SEAT,Lamination，230025，T,Equipment | 陈佳荣 | 周华盛 | Post Launch |  | / | B | B | B | / | R | / | 2022-12-30 | 2023-01-30 | 2023-07-01 | 230025
30017310-EBP | 30017310;2024,AP,Brilliance-BMW,G48-SEAT,lamination，230026，T,Equipment | 陈佳荣 | 周华盛 | Post Launch |  | / | B | B | B | / | R | / | 2023-01-29 | 2023-03-01 | 2023-07-01 | 230026
30017301-EBP | 30017301-2024,AP,Brilliance-BMW,G4x-Binc, EOL,30013967, M,Equipment | 邱伯超 | 黄定辉 | Phase Out |  | / | B | B | B | / | R | / | 2023-04-10 | 2023-04-17 | 2023-05-31
30017299-EBP | 30017299;2024,AP,VW Group,VW491-DP,lamination,230184,M,Equipment | 尚兵 | 陈斌 | Phase Out |  | / | B | B | B | / | R | / | 2023-08-02 | 2023-09-01 | 2023-09-08 | 230184
30017293-EBP | 30017293;2024,AP,Li Auto,W01-A pillar,Lamination,230225,T,Equipment | 尚兵 | 阚城奔 | Phase Out |  | / | B | B | B | / | R | / | 2023-09-29 | 2023-10-14 | 2023-12-05 | 230225
30017283-EBP | 30017283;2024,AP,BAIC,CK71KB-Ambient,Milling,230207,M,Equipment | 孟子冰 | 陈志斌 | Phase Out |  | / | B | B | B | / | R | / | 2023-10-31 | 2023-12-30 | 2023-12-31 | 230207
30017257-EBP | 30017257-2024,AP,BYD,BYD HK DP-220340-M,Equipment | 尚兵 | 刘佳佳 | Cancel/Pending |  | / | R | R | R | / | / | / | 2023-11-10 | 2023-11-17 | 2024-05-17 | 220340
30017256-EBP | 30017256-2025,AP,Tes,Cyberturck-IP, CHYM,230081,M,Equipment | 龚胜超 | 黄定辉 | Phase Out |  | / | B | B | B | / | R | / | 2023-10-13 | 2023-11-30 | 2023-12-28 | 230081
30017255-EBP | 30017255;2024,AP,Tes,NV26-DP, welding, 230221, 1T,Equipment | 王保卫 | 杜全喆 | Phase Out |  | / | B | B | B | / | R | 无重大安全问题 发运前安全分97.06% | 2023-09-25 | 2024-06-10 | 2024-06-30 | 230221
30017245-EBP | 30017245;2025,AP,Daimler,BR223-DP,Equipment | 赵军 | 陈斌 | Cancel/Pending |  |  | R | R | R |  |  | 取消 | 2025-07-26 | 2025-08-26 | 2025-09-25
30017228-EBP | 30017228;2025,AP,Daimler,BR223-DP,Pre-fixing,230170,T,Equipment | 赵军 | 陈斌 | Phase 5 Production Delivery |  | / | B | B | B | / | B | 完成 | 2023-12-29 | 2024-01-31 | 2024-09-24 | 230170
30017227-EBP | 30017227;2025,AP,Daimler,BR223-DP,Pre-fixing,230169,M,Equipment | 赵军 | 陈斌 | Phase 5 Production Delivery |  | / | B | B | B | / | B | 完成 | 2023-11-10 | 2024-08-09 | 2024-10-11 | 230169
30017226-EBP | 30017226-2025,AP,Daimler,BR223-DP,Lamination,230219,T,Equipment | 赵军 | 赵书泰 | Post Launch |  | / | B | B | B | / | B | / | 2023-12-29 | 2024-01-19 | 2024-08-23 | 230219
30017225-EBP | 30017225-2025,AP,Daimler,BR223-DP,Lamination,230218,T,Equipment | 赵军 | 赵书泰 | Post Launch |  | / | B | B | B | / | B | / | 2023-12-29 | 2024-01-19 | 2024-08-23 | 230218
30017224-EBP | 30017224-2025,AP,Daimler,BR223-DP,Lamination,230217,T,Equipment | 赵军 | 赵书泰 | Post Launch |  | / | B | B | B | / | B | / | 2023-12-29 | 2024-01-26 | 2024-08-23 | 230217
30017223-EBP | 30017223-2025,AP,Daimler,BR223-DP,Lamination,230210,T,Equipment | 赵军 | 樊爱强 | Post Launch |  | / | B | B | B | / | R | / | 2023-12-29 | 2024-01-26 | 2024-08-09 | 230210
30017222-EBP | 30017222-2025,AP,Daimler,BR223-DP,Lamination,230215,T,Equipment | 赵军 | 赵书泰 | Post Launch |  | / | B | B | B | / | B | / | 2023-12-29 | 2024-01-26 | 2024-08-23 | 230215
30017221-EBP | 30017221-2025,AP,Daimler,BR223-DP,Lamination,230216,T,Equipment | 赵军 | 赵书泰 | Post Launch |  | / | B | B | B | / | B | / | 2023-12-29 | 2024-01-26 | 2024-08-23 | 230216
30017219-EBP | 30017219-2025,AP,Daimler,BR223-DP,Lamination,230214,T,Equipment | 赵军 | 赵书泰 | Post Launch |  | / | B | B | B | / | B | / | 2023-12-29 | 2024-01-26 | 2024-08-23 | 230214
30017218-EBP | 30017218-2025,AP,Daimler,BR223-DP,Lamination,230211,T,Equipment | 赵军 | 樊爱强 | Post Launch |  | / | B | B | B | / | R | / | 2023-12-29 | 2024-01-26 | 2024-08-09 | 230211
30017211-EBP | 30017211-2025,AP,Daimler,BR223-DP,Lamiination,230209,T,Equipment | 赵军 | 樊爱强 | Post Launch |  | / | B | B | B | / | R | / | 2023-12-29 | 2024-01-26 | 2024-08-09 | 230209
30017184-EBP | 30017184-2025,AP,Daimler,BR223-DP,Lamination,230213,M,Equipment | 赵军 | 陈斌 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-09-29 | 2023-10-09 | 2024-08-09 | 230213
30017183-EBP | 30017183-2025,AP,Daimler,BR223-DP,Lamination,230212,M,Equipment | 赵军 | 陈斌 | Post Launch |  | / | B | B | B | / | R | / | 2023-10-06 | 2023-10-13 | 2024-08-02 | 230212
30017178-EBP | 30017178-2024,AP,Daimler,MBEAM-IP,CUN Lamination,230067,M,Equipment | 白宇鹏 | 陈洁 | Phase Out |  | / | B | B | B | 车间 | R | / | 2024-01-27 | 2024-04-19 | 2024-07-06 | 230067
30017177-EBP | 30017177-2024,AP,Daimler,MBEAM-IP,CUN Lamination,230068,T,Equipment | 白宇鹏 | 陈子翌 | Phase Out |  | / | B | B | B | / | R | / | 2024-01-27 | 2024-04-19 | 2024-07-06 | 230068
30017176-EBP | 30017176-2024,AP,Daimler,MBEAM-DP,MF Lamination,230120,T,Equipment | 白宇鹏 | 高一恒 | Post Launch |  | / | B | B | B | / | R | / | 2024-01-27 | 2024-04-19 | 2024-06-08 | 230120
30017175-EBP | 30017175-2024,AP,Daimler,MBEAM-DP,MF Lamination,230119,1T,Equipment | 白宇鹏 | 高一恒 | Post Launch |  | / | B | B | B | / | / | / | 2024-01-27 | 2024-04-19 | 2024-06-08 | 230119
30017174-EBP | 30017174;2024,AP,Daimler,MBEAM-DP,MF Lamination,230118,T,Equipment | 白宇鹏 | 闵宏恩 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2024-01-27 | 2024-04-19 | 2024-06-08 | 230118
30017173-EBP | 30017173-2024,AP,Daimler,MBEAM-DP,MF Lamination,230117,T,Equipment | 白宇鹏 | 闵宏恩 | Post Launch |  | / | B | B | B | / | R | / | 2024-01-27 | 2024-04-19 | 2024-06-08 | 230117
30017172-EBP | 30017172-2024,AP,Daimler,MBEAM-IP US welding,230093,T,Equipment | 白宇鹏 | 邱永旭 | Phase0 |  | / | B | B | B | / | / | / | 2024-01-27 | 2024-04-19 | 2024-06-28 | 230093
30017171-EBP | 30017171-2024,AP,Daimler,MBEAM-IP,US welding,230092,T,Equipment | 白宇鹏 | 邱永旭 | Phase0 |  | / | B | B | B | / | R | / | 2024-01-27 | 2024-04-19 | 2024-06-28 | 230092
30017170-EBP | 30017170-2024,AP,Daimler,MBEAM-IP,US Welding,230091,T,Equipment | 白宇鹏 | 邱永旭 | Phase0 |  | / | B | B | B | / | R | / | 2024-03-15 | 2024-04-13 | 2024-07-06 | 230091
30017123-EBP | 30017123;2024,AP,Volvo Group Global,723D-Pillar,Lamination,230138,T,Equipment | 邹成成 | 方志伟 | Phase Out |  | / | B | B | B | / | R | / | 2023-06-07 | 2023-07-12 | 2024-02-29 | 230138
30017118-EBP | 30017118;2024,AP,Volvo Group Global,723D-Pillar,Lamination,230137,T,Equipment | 邹成成 | 方志伟 | Phase Out |  | / | B | B | B | / | R | / | 2023-06-07 | 2023-07-12 | 2024-02-29 | 230137
30017117-EBP | 30017117;2024,AP,Volvo Group Global,723D-Pillar,Lamination,230136,T,Equipment | 邹成成 | 方志伟 | Phase Out |  | / | B | B | B | / | R | / | 2023-06-07 | 2023-07-12 | 2024-02-29 | 230136
30017116-EBP | 30017116;2024,AP,General Motors,SGM358-DP,Edge-folding,230158,T,Equipment | 邹成成 | 陈子翌 | Phase Out |  | / | B | B | B | / | R | / | 2023-07-20 | 2023-07-29 | 2024-03-08 | 230158
30017115-EBP | 30017115;2024,AP,General Motors,SGM358-DP,Edge-folding,230157,T,Equipment | 邹成成 | 陈子翌 | Phase Out |  | / | B | B | B | / | R | / | 2023-07-20 | 2023-07-29 | 2024-03-08 | 230157
30017113-EBP | 30017113-2024,AP,SAIC-VW,VW426-DP,Lamination,230162,T,Equipment | 邹成成 | 金宇隆 | Phase Out |  | / | B | B | B | / | R | / | 2023-08-01 | 2023-08-31 | 2024-04-30 | 230162
30017111-EBP | 30017111-2024,AP,SAIC-VW,VW426-DP,Lamination,230161,T,Equipment | 邹成成 | 金宇隆 | Phase Out |  | / | B | B | B | / | R | / | 2023-08-01 | 2023-08-31 | 2024-04-30 | 230161
30017110-EBP | 30017110;2024,AP,SAIC-VW,VW426-DP,Lamination,230160,T,Equipment | 邹成成 | 王星 | Phase Out |  | / | B | B | B | / | R | / | 2023-08-01 | 2023-08-31 | 2024-04-30 | 230160
30017109-EBP | 30017109;2024,AP,SAIC-General Motors-Wuling,D2UC-DP,Lamination,230154,T,Equipment | 邹成成 | 方志伟 | Phase Out |  | / | B | B | B | / | R | / | 2023-07-20 | 2023-08-01 | 2024-03-08 | 230154
30017108-EBP | 30017108;2024,AP,Tes,Highland-FC, ASSYLine, 220343, M,Equipment | 王保卫 | 赵凯亮 | Phase Out |  | / | B | B | B | / | R | / | 2023-03-01 | 2023-04-01 | 2023-05-31 | 220343
30017107-EBP | 30017107;2024,NA,General Motors,L232-DP,EOL,230058,M,Equipment | 王翔 | 程德宝 | Phase Out |  | / | B | B | B | / | R | / | 2023-03-16 | 2023-03-28 | 2023-06-28 | 230058
30017101-EBP | 30017101;2024,AP,smartmi,MS11-IP,Edge-folding,230205,T,Equipment | 邹成成 | 陈斌 | Phase Out |  | / | B | B | B | / | R | / | 2023-08-31 | 2023-09-21 | 2024-02-29 | 230205
30017099-EBP | 30017099;2024,AP,smartmi,MS11-IP,Edge-folding,230204,M,Equipment | 邹成成 | 陈斌 | Phase Out |  | / | B | B | B | / | R | / | 2023-08-31 | 2023-09-21 | 2024-02-29 | 230204
30017098-EBP | 30017098-2024,AP,Daimler,MBEAM-IP,US WELDING,230090,T,Equipment | 白宇鹏 | 邱永旭 | Phase0 |  | / | B | B | B | / | / | / | 2024-03-02 | 2024-03-30 | 2024-07-06 | 230090
30017095-EBP | 30017095-2025,AP,Daimler,BR223-DP,Glue Spray,230190,T,Equipment | 赵军 | 陈志斌 | Post Launch |  | / | B | B | B | / | R | / | 2023-12-29 | 2024-01-12 | 2024-12-06 | 230190
30017084-EBP | 30017084;2023,AP,BAIC ORV,C71KB-IP,lamination,230177,T,Equipment | 夏阳 | 王星 | Post Launch |  | / | B | B | B | / | R | / | 2024-01-31 | 2024-04-10 | 2024-05-31 | 230177
30017079-EBP | 30017079;2024,AP,General Motors,L234-FC, Lamination, 230126, 2T,Equipment | 王保卫 | 韦少官 | Phase Out |  | / | B | B | B | / | R | / | 2023-08-05 | 2023-08-25 | 2023-10-15 | 230126
30017077-EBP | 30017077;2023,AP,SAIC-GM,C1YB2-IP, Lamination, 220219,T,Equipment | 邱伯超 |  | Cancel/Pending |  | / | R | R | R | / | / | / | 2023-11-05 | 2023-12-06 | 2024-01-05 | 220219
30017076-EBP | 30017076;2024,AP,smartmi,MS11-IP,Edge-folding,220112,T,Equipment | 邹成成 | 黄东方 | Phase Out |  | / | B | B | B | / | R | / | 2023-05-04 | 2023-05-13 | 2023-08-04 | 220112
30017056-EBP | 30017056;2024,AP,BAIC,C71KB-A-Llight, EOL, 230200, 2T,Equipment | 孟子冰 | 周理文 | Phase Out |  | / | B | B | B | / | R | / | 2023-09-02 | 2023-09-22 | 2023-11-01 | 230200
30017050-EBP | 30017050;2024,AP,smartmi,MS11-IP,Edge-folding,230111,T,Equipment | 邹成成 | 黄东方 | Phase Out |  | / | B | B | B | / | R | / | 2023-05-04 | 2023-05-13 | 2023-08-04 | 230111
30017048-EBP | 30017048;2024,AP,smartmi,MS11-IP,Edge-folding,230110,M,Equipment | 邹成成 | 陈斌 | Phase Out |  | / | B | B | B | / | R | / | 2023-05-04 | 2023-05-13 | 2023-08-04 | 230110
30017034-EBP | 30017034;2023,NA,Mazda,J34H-CNSL,Assembly,220260,T,Equipment | 王翔 | 赵凯亮 | Phase Out |  | / | B | B | B | / | R | / | 2022-11-11 | 2023-01-15 | 2023-02-28 | 220260
30017033-EBP | 30017033-2024,AP,BMW,G4X -Lbar,EOL,230201,3M,Equipment | 孟子冰 | 冯全华 | Phase0 |  | / | B | B | B | / | R | / | 2023-11-03 | 2024-02-29 | 2024-04-27 | 230201
30017023-EBP | 30017023;2024,AP,General Motors,L234-Seatback,welding,230001,1T,Equipment | 王保卫 | 郝秀霞 | Phase Out |  | / | B | B | B | / | R | / | 2023-04-01 | 2023-04-01 | 2023-05-01 | 230001
30017009-EBP | 30017009;2024,AP,VW Group,E4-FC, Clipping, 230123, T,Equipment | 樊皆杰 | 高大尉 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-05-10 | 2023-08-10 | 2024-02-25 | 230123
30017006-EBP | 30017006;2024,AP,VW Group,E4-FC,Clipping,230123,M,Equipment | 樊皆杰 | 杜全喆 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-05-30 | 2023-07-01 | 2024-03-18 | 230123
30017005-EBP | 30017005-2024,AP,VW Group,E4-FC,Welding,230079,M,Equipment | 樊皆杰 | 郝秀霞 | Phase0 |  | / | B | B | B | / | R | / | 2023-04-10 | 2023-05-10 | 2024-01-10 | 230079
30017004-EBP | 30017004;2024,AP,VW Group,E4-FC,Welding,230083,T,Equipment | 樊皆杰 | 郝秀霞 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-08-15 | 2023-09-17 | 2024-02-01 | 230083
30017003-EBP | 30017003;2024,AP,VW Group,E4-FC,Welding.230082,M,Equipment | 樊皆杰 | 郝秀霞 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-05-10 | 2023-05-30 | 2024-02-01 | 230082
30017002-EBP | 30017002;2024,AP,VW Group,E4-DP,Pre-fixing,230128,T,Equipment | 樊皆杰 | 王星 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-07-10 | 2023-08-22 | 2024-07-31 | 230128
30017001-EBP | 30017001;2024,AP,VW Group,E4-DP,Pre-fixing,230128,M,Equipment | 樊皆杰 | 王星 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-07-10 | 2023-07-25 | 2024-07-31 | 230128
30016998-EBP | 30016998-2024,AP,VW Group,E4-DP,welding,230127,T,Equipment | 樊皆杰 | 高大尉 | Phase0 |  | / | B | B | B | / | R | / | 2023-08-10 | 2023-08-20 | 2023-09-24 | 230127
30016970-EBP | 30016970-2024,AP,Daimler,MBEAM-DP,Lamination,230070,T,Equipment | 白宇鹏 |  | Phase Out |  | / | B | B | B | / | R | / | 2024-04-13 | 2024-04-20 | 2024-06-08 | 230070
30016969-EBP | 30016969;2024,AP,Daimler,MBEAM-DP,Lamination,230069,M,Equipment | 白宇鹏 | 陈斌 | Phase Out |  | / | B | B | B | / | R | / | 2023-09-22 | 2023-10-21 | 2024-02-01 | 230069
30016955-EBP | 30016955-2025,AP,Daimler,BR223-DP,Glue Spray,230192,M,Equipment | 赵军 | 陈志斌 | Post Launch |  | / | B | B | B | / | B | 完成 | 2023-12-29 | 2026-01-29 | 2026-02-12 | 230192
30016954-EBP | 30016954-2025,AP,Daimler,BR223-DP,Glue Spray,230189,M,Equipment | 赵军 | 陈志斌 | Post Launch |  | / | B | B | B | / | B | / | 2023-12-29 | 2024-01-19 | 2024-09-30 | 230189
30016953-EBP | 30016953;2025,AP,Daimler,BR223-DP,Lamination,230180,T,Equipment | 赵军 | 樊爱强 | Phase 5 Production Delivery |  | / | B | B | B | / | / | / | 2023-12-29 | 2024-01-26 | 2024-07-20 | 230180
30016923-EBP | 30016923-2025,AP,Daimler,BR223-DP,Lamination,230179,M,Equipment | 赵军 | 陈斌 | Post Launch |  | / | B | B | B | / | / | 完成 | 2023-11-01 | 2023-12-12 | 2024-07-29 | 230179
30016848-EBP | 30016848-2024,AP,Audi FAW NEV,A6-DP,Clipping,230197,M,Equipment | 杨阳 | 王万芳 | Phase Out |  | / | B | B | B | / | B | 完成 | 2023-05-31 | 2023-09-30 | 2024-12-31 | 230197
30016847-EBP | 30016847;2025,AP,BMW,NCAR-IP,Welding,230188,T,Equipment | 杨阳 | 郝秀霞 | Post Launch |  | / | B | B | B | 遗留 | R | 完成 | 2023-05-31 | 2024-01-31 | 2024-11-30 | 230188
30016846-EBP | 30016846;2025,AP,BMW,NCAR-IP,Welding,230187,M,Equipment | 杨阳 | 郝秀霞 | Post Launch |  | / | B | B | B | / | R | / | 2023-05-26 | 2024-01-31 | 2024-06-30 | 230187
30016843-EBP | 30016843;2025,AP,BMW,NCAR-IP,Lamination,230109.T,Equipment | 杨阳 | 阚城奔 | Phase Out |  | / | B | B | R | / | R | / | 2023-10-05 | 2024-02-09 | 2024-07-31 | 230109
30016842-EBP | 30016842-2025,AP,BMW,NCAR-IP,Lamination,230108,M,Equipment | 杨阳 | 陈洁 | Phase Out |  | / | B | B | B | / | / | / | 2023-10-06 | 2024-03-31 | 2024-07-31 | 230108
30015126-EBP | 30015126;2023,AP,VW Group,E4-DP,Screwing,230101,T,Equipment | 樊皆杰 | 高大尉 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-06-30 | 2023-07-20 | 2024-04-22 | 230101
30015125-EBP | 30015125;2023,AP,VW Group,E4-DP,Screwing,230100,M,Equipment | 樊皆杰 | 刘璟华 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-05-31 | 2023-06-30 | 2024-04-25 | 230100
30014653-EBP | 30014653;2023,AP,Daimler,MBEAM-DP,Glue-spray,230072,1T,Equipment | 白宇鹏 | 刘佳佳 | Phase Out |  | / | B | B | B | / | R | / | 2024-04-13 | 2024-04-27 | 2024-06-08 | 230072
30014652-EBP | 30014652-2023,AP,Daimler,MBEAM-DP,Glue-spray,230071,1M,Equipment | 白宇鹏 | 刘佳佳 | Phase Out |  | / | B | B | B | / | R | / | 2024-04-27 | 2024-05-11 | 2024-06-08 | 230071
30014414-EBP | 30014414;2023,AP,General Motors,L232-DP,Welding,230057,T,Equipment | 王翔 | 高大尉 | Phase Out |  | / | B | B | B | / | R | / | 2023-03-20 | 2023-04-07 | 2023-07-14 | 230057
30014413-EBP | 30014413;2023,AP,General Motors,L232-DP,Welding,230056,T,Equipment | 王翔 | 高大尉 | Phase Out |  | / | B | B | B | / | R | / | 2023-03-20 | 2023-04-07 | 2023-07-14 | 230056
30014412-EBP | 30014412;2023,AP,General Motors,L232-DP,Welding,230055,T,Equipment | 王翔 | 高大尉 | Phase Out |  | / | B | B | B | / | R | / | 2023-03-20 | 2023-04-07 | 2023-07-14 | 230055
30014411-EBP | 30014411;2023,AP,General Motors,L232-DP,Welding,230054,T,Equipment | 王翔 | 高大尉 | Phase Out |  | / | B | B | B | / | R | / | 2023-03-20 | 2023-04-07 | 2023-07-14 | 230054
30014402-EBP | 30014402;2023,AP,General Motors,L232-DP,Welding,230053,M,Equipment | 王翔 | 赵凯亮 | Phase Out |  | / | B | B | B | / | R | / | 2023-03-03 | 2023-03-16 | 2023-07-14 | 230053
30014401-EBP | 30014401;2023,AP,General Motors,L232-DP,Welding,230051,M,Equipment | 王翔 | 赵凯亮 | Phase Out |  | / | B | B | B | / | R | / | 2023-03-03 | 2023-03-16 | 2023-07-14 | 230051
30013159-EBP | 30013159;2023,AP,Geely-Volvo,V551K-IP,Welding,230008,T,Equipment | 夏阳 |  | Post Launch |  | / | B | B | B | / | R | / | 2023-03-16 | 2023-04-16 | 2023-05-16 | 230008
30013158-EBP | 30013158;2023,AP,Geely-Volvo,V551K-IP,Welding,230007,T,Equipment | 夏阳 |  | Post Launch |  | / | B | B | B | / | R | / | 2023-03-16 | 2023-04-16 | 2023-05-16 | 230007
30013157-EBP | 30013157;2023,AP,Geely-Volvo,V551K-IP,Welding,230006,T,Equipment | 夏阳 |  | Post Launch |  | / | B | B | B | / | R | / | 2023-03-16 | 2023-04-16 | 2023-05-16 | 230006
30013145-EBP | 30013145;2023,AP,VW Group,E4-DP,Gluing,230017,T,Equipment | 樊皆杰 | 刘佳佳 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-03-01 | 2023-04-01 | 2023-12-05 | 230017
30013144-EBP | 30013144;2023,AP,VW Group,E4-DP,Gluing,230016,M,Equipment | 樊皆杰 | 刘佳佳 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-03-01 | 2023-04-01 | 2023-12-05 | 230016
30013132-EBP | 30013132;2023,AP,VW Group,E4-DP,Lamination,230014,T,Equipment | 樊皆杰 | 陈子翌 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-03-01 | 2023-04-01 | 2023-11-10 | 230014
30013130-EBP | 30013130;2023,AP,VW Group,E4-DP,Lamination,230012,T,Equipment | 樊皆杰 | 陈子翌 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-02-10 | 2023-03-30 | 2023-11-10 | 230012
30013129-EBP | 30013129;2023,AP,VW Group,E4-DP,Lamination,230011,T,Equipment | 樊皆杰 | 陈子翌 | Phase 5 Production Delivery |  | / | B | B | B | / | R | / | 2023-03-01 | 2023-04-01 | 2023-11-10 | 230011
30011955-EBP | 30011955-2022,AP,YFITC-Internal,MMA-IP,Welding,220269,M,Equipment | 郭正阳 | 陈晓春 | Phase Out |  | / | B | B | B | / | B | 欧洲本地利旧设备 | 2025-12-20 | 2025-12-25 | 2025-12-30 | 220269
30031093-EBP | 30031093-2025,AP,XPENG,JH-A-sun visor,assy,250321,Equipment | 王保卫 | 王晓宇 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-12-13 | 2025-12-31 | 2026-02-28 | 250321
30031061-EBP | 30031061;2025,AP,Daimler,V530-IP,EOAT,250318,2T,Equipment | 杨阳 | 王晓宇 | Phase 4 Manufacturing Development | 2025-11-03 |  | R | R | R |  |  | 无重大安全问题 发运前安全分96.88% | 2025-10-31 | 2025-11-30 | 2025-12-31 | 250318
30031048-EBP | 30031048-2025,AP,XPENG,JH-A-mirror,assy,250317,1M,Equipment | 王保卫 | 韦少官 | Phase 5 Production Delivery |  |  | R | R | R |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-12-11 | 2026-01-11 | 2026-02-10 | 250317
30031044-EBP | 30031044-2026,NA,Tes,NV26-DP, welding,250316,T,Equipment | 王翔 | 刘璟华 | Post Launch | 2025-10-24 |  | R | R | R |  |  | 无重大安全问题 发运前安全分97.06% | 2025-10-30 | 2025-11-13 | 2026-02-28 | 250316
30030948-EBP | 30030948-2026,AP,Jianghuai,JH-1,Glue,250313,M,Equipment | 王保卫 | 陈洁 | Phase0 | 2025-12-26 |  | R | R | R |  |  | 无重大安全问题 85.34% | 2025-10-31 | 2025-11-15 | 2026-01-09 | 250313
30031042-EBP | 30031042-2026,AP,XPENG,G02-Vent,EOL,250315,T,Equipment | 王翔 | 周理文 | Phase 4 Manufacturing Development | 2025-09-16 |  | R | R | R |  |  | 无重大安全问题 发运前安全分96.67% | 2025-10-31 | 2025-11-20 | 2026-03-31 | 250315
30031260-EBP | 30031260-2025,AP,SERES Motors,X1L Sunvisor Assy tool,250325,T,Equipment | 孟子冰 | 周华盛 | Phase 5 Production Delivery |  |  | R | R | R |  |  | 无重大安全问题 发运前安全分96.43% | 2025-12-26 | 2026-01-26 | 2026-02-25 | 250325
30030744-EBP | 30030744-2028,AP,BMW,G66-side bolster,weld,250309,T,Equipment | 樊皆杰 | 刘璟华 | Phase 5 Production Delivery | 2025-11-11 |  | R | R | R |  |  | 无重大安全问题 发运前安全分96.97% | 2025-11-10 | 2025-11-20 | 2026-02-05 | 250309
30030743-EBP | 30030743-2028,AP,BMW,G66-side bolster,lam,250308,T,Equipment | 樊皆杰 | 阚城奔 | Post Launch | 2025-10-28 |  | R | R | R |  |  | 无重大安全问题 发运前安全分96.97% | 2025-11-05 | 2025-11-06 | 2026-01-20 | 250308
30031304-EBP | 30031304-2026,AP,Chery,EHV-Pilla,Welding,250319,1M,Equipment | 夏阳 | 黄圣 | Phase 1 Quotation | 2025-12-02 |  | G | G | G |  |  | 无重大安全问题 100% | 2026-05-31 | 2026-06-30 | 2026-07-31 | 250319
30030581-EBP | 30030581-2025,AP,XPENG,B-SUV-mirror,assembly,250298, XT,Equipment | 王保卫 | 陈志斌 | Phase 4 Manufacturing Development | 2026-03-05 |  | R | R | R |  |  |  | 2026-01-28 | 2026-03-11 | 2026-03-30 | 250298
30031536-EBP | 30031536-2026,AP,Huawei Anhui,EHV-DP,Lamination,250337,T,Equipment | 夏阳 | 樊爱强 | Phase 3 Design Feasibility |  |  | R | R | G |  |  | 无重大安全问题 发运前安全分94.59% | 2026-01-10 | 2026-04-30 | 2026-08-31 | 250337
30031525-EBP | 30031525-2027,EMEA,Mercedes-Benz,EU V530-cun,pre-fixing,250334,M,Equipment | 樊皆杰 | 黄琳健 | Phase 4 Manufacturing Development |  |  | R | R | Y |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-12-19 | 2025-12-20 | 2026-05-20 | 250334
30031505-EBP | 30031505-2025,AP,SVW,B-SUV-mirror,assy,250332,1M,Equipment | 王保卫 | 陈志斌 | Phase 4 Manufacturing Development | 2025-11-14 |  | R | R | R |  |  | 无重大安全问题 发运前安全分87.9% | 2025-11-20 | 2025-11-30 | 2026-01-20 | 250332
30031593-EBP | 30031593-2026,AP,SERES Motors,F2N 副遮阳板EOL,250341,MT,Equipment | 孟子冰 | 王晓宇 | Phase 5 Production Delivery |  |  | R | R | R |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-12-15 | 2025-12-31 | 2026-03-31 | 250341
30031526-EBP | 30031526-2027,EMEA,Mercedes-Benz,EU V530 CUN,pre-fixing,250335,T,Equipment | 樊皆杰 | 陈雨杭 | Phase 4 Manufacturing Development | 2025-12-16 |  | R | R | Y |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-12-20 | 2025-12-20 | 2026-05-20 | 250335
30031623-EBP | 30031623-2026,AP,SAIC-VW,VW311-6-IP, Spary, 250344, M,Equipment | 袁帅 | 陈洁 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  |  | 2026-01-30 | 2026-02-27 | 2026-03-27 | 250344
30031621-EBP | 30031621-2026,AP,BYD,HC-BYD,SA3,Spary,250343,M,Equipment | 孟子冰 | 陈洁 | Phase 5 Production Delivery |  |  | R | R | R |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-12-31 | 2026-01-16 | 2026-01-30 | 250343
30031687-EBP | 30031687-2027,AP,SAIC,SHB-IP, assy, 250349, M,Equipment | 袁帅 | 李彦辰 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  |  | 2026-01-30 | 2026-02-27 | 2026-03-30 | 250349
30031858-EBP | 30031858-2027,AP,SAIC,SHB-IP, Clip, 250356, T,Equipment | 袁帅 | 郝秀霞 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  |  | 2026-01-30 | 2026-02-27 | 2026-03-30 | 250356
30031857-EBP | 30031857-2027,AP,SAIC,SHB-IP, Clip, 250355, M,Equipment | 袁帅 | 郝秀霞 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  |  | 2026-01-30 | 2026-02-27 | 2026-03-30 | 250355
30031541-EBP | 30031541-2026,AP,Huawei Anhui,EHV-DP,Lamination,250340,T,Equipment | 夏阳 |  | Post Launch |  |  | G | G | G |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-05-31 | 2026-06-30 | 2026-07-31 | 250340
30031540-EBP | 30031540-2026,AP,Huawei Anhui,EHV-DP,Lamination,250339,T,Equipment | 夏阳 | 樊爱强 | Phase 1 Quotation | 2025-12-01 |  | G | G | G |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-05-30 | 2026-06-30 | 2026-07-31 | 250339
30031537-EBP | 30031537-2026,AP,Huawei Anhui,EHV-DP,Lamination,250338,T,Equipment | 夏阳 | 樊爱强 | Post Launch |  |  | G | G | G |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-05-30 | 2026-06-30 | 2026-07-31 | 250338
30031949-EBP | 30031949-2025,AP,BYD, 深汕-Roller,250359,M,Equipment | 孟子冰 | 陈洁 | Phase 5 Production Delivery | 2026-02-02 |  | R | R | R |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-01-08 | 2026-01-30 | 2026-03-23 | 250359
30030313-EBP | 30030313-2026,AP,Tes,Highland-FC,Assembly,250268,3T,Equipment | 龚胜超 | 王晓宇 | Phase0 |  |  | R | G | G |  |  |  | 2026-02-10 | 2026-07-22 | 2026-09-22 | 250268
30032531-EBP | 30032531-2026,AP,SERES Motors,F2N-DAB, Lamination, 250383, T,Equipment | 邹成成 | 黄东方 | Phase 4 Manufacturing Development | 2026-02-11 |  | R | R | G |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-03-21 | 2026-04-15 | 2026-06-30 | 250383
30032635-EBP | 30032635-2026,AP,SERES Motors,V32&K89-IP, spray, 260003, M,Equipment |  | 陈洁 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  |  | 2026-02-27 | 2026-03-30 | 2026-04-30 | 260003
30032527-EBP | 30032527-2026,AP,SERES Motors,A15-CNSL, EOL, 250384, M,Equipment |  | 冯全华 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  |  | 2026-02-27 | 2026-03-30 | 2026-04-30 | 250384
30032362-EBP | 30032362-2026,AP,BYD,ST+MR-IP, assy, 250375, M,Equipment |  | 李彦辰 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  |  | 2026-02-27 | 2026-03-30 | 2026-04-30 | 250375
30032046-EBP | 30032046-2026,AP,smartmi,MX-light,250362,M,Equipment |  | 郝秀霞 | Phase 5 Production Delivery | 2026-03-05 |  | R | R | R |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-03-06 | 2026-03-18 | 2026-04-17 | 250362
30016849-EBP | 30016849-2024,AP,Audi FAW NEV,A6-DP,Clipping,230198,T,Equipment | 杨阳 | 王万芳 | Phase Out |  |  | R | R | R |  |  |  | 2023-05-31 | 2023-09-30 | 2024-12-31 | 230198
30017125-EBP | 30017125-2024,AP,SERES Motors,F2-DAB,Lamination,220332,M,Equipment | 邹成成 | 阚城奔 | Terminated |  |  | R | R | R |  |  |  | 2026-03-01 | 2026-04-01 | 2026-05-01 | 220332
30033461-EBP | 30033461-2026,AP,SVW,B-SUV-mirror,assy,260041,1M,Equipment |  | 陈志斌 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-05-30 | 2026-06-30 | 2026-07-31 | 260041
30033404-EBP | 30033404-2026,AP,VW Group,VW426-DP,Lamination,260033,M,Equipment |  | 黄琳健 | Phase 3 Design Feasibility |  |  | R | R | G |  |  |  | 2026-04-09 | 2026-05-10 | 2026-06-09 | 260033
30033043-EBP | 30033043-2027,AP,General Motors,C1UL-IP,Lamination,260020,T,Equipment |  | 高一恒 | Phase 1 Quotation | 2026-02-11 |  | G | G | G |  |  |  | 2026-07-28 | 2026-08-28 | 2026-09-27 | 260020
30032991-EBP | 30032991-2026,AP,Jianghuai,JH-C-mirror,assembly,260009,14T,Equipment |  | 张帅 | Phase 4 Manufacturing Development |  |  | R | R | G |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-03-21 | 2026-04-21 | 2026-05-21 | 260009
30032988-EBP | 30032988-2026,AP,SERES Motors,V32-mirror,Assembly,260007, 14T,Equipment |  | 郭新杰 | Phase 4 Manufacturing Development |  |  | R | R | G |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-03-21 | 2026-04-21 | 2026-05-21 | 260007
30032915-EBP | 30032915-2026,AP,Renault-Nissan-Mitsubishi,R758&R745-CNSL,test,260014,M,Equipment |  | 王万芳 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-05-29 | 2026-06-29 | 2026-08-31 | 260014
30032909-EBP | 30032909-2026,AP,SERES Motors,F2N10lm-light,assemble,260017,T,Equipment |  | 周理文 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  |  | 2026-03-30 | 2026-04-17 | 2026-04-30 | 260017
30032706-EBP | 30032706-2025,AP,SERES Motors,A15-mirror, assy, 260006, 15T,Equipment |  | 王万芳 | Phase 1 Quotation |  |  | R | G | G |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-05-10 | 2026-05-31 | 2026-06-30 | 260006
30032543-EBP | 30032543-2026,AP,smartmi,F2N-light,assemble,250363,T,Equipment |  | 黄圣 | Phase 3 Design Feasibility |  |  | R | R | G |  |  |  | 2026-03-30 | 2026-04-30 | 2026-05-30 | 250363
30032370-EBP | 30032370-2026,AP,SERES Motors,F3_Seat rail,Assy,250379,Equipment |  | 黄定辉 | Phase 3 Design Feasibility |  |  | R | R | G |  |  |  | 2026-03-31 | 2026-05-01 | 2026-08-31 | 250379
30032067-EBP | 30032067-2025,AP,XPENG,G02顶棚EOL ,250364,1M2T,Equipment |  | 黄圣 | Phase 4 Manufacturing Development |  |  | R | R | R |  |  |  | 2026-04-14 | 2026-04-15 | 2026-04-30 | 250364
30033578-EBP | 30033578-2026,AP,Tes,TBD_Click Rim, Lami, 260050, T,Equipment |  | 周华盛 | Phase 2 Concept Definition |  |  | R | G | G |  |  |  | 2026-05-12 | 2026-06-12 | 2026-08-31 | 260050
30033539-EBP | 30033539-2026,AP,DF-Liuzhou,F05-CNSL,Lamination,260044,MLA,Equipment |  | 黄琳健 | Phase 4 Manufacturing Development | 2026-03-25 |  | R | R | R |  |  |  | 2026-03-14 | 2026-03-28 | 2026-04-30 | 260044
30033537-EBP | 30033537-2026,AP,Guangzhou Auto,F03,DP,Lamination,260045,M,Equipment |  | 黄琳健 | Phase 4 Manufacturing Development | 2026-03-20 |  | R | R | R |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-03-13 | 2026-03-20 | 2026-04-30 | 260045
30033723-EBP | 30033723-2026,AP,VW Group,VW426 PAB Chute Cell CI,260042,M,Equipment |  | 韦少官 | Phase 2 Concept Definition |  |  | R | G | G |  |  |  | 2026-05-01 | 2026-06-01 | 2026-07-01 | 260042
30031771-EBP | 30031771-2025,AP,SAIC-VW,416-light,assemble，250353，T,Equipment | 陈佳荣 | 黄圣 | Phase 5 Production Delivery | 2026-03-02 |  | R | R | R |  |  |  | 2026-04-10 | 2026-03-07 | 2026-03-14 | 250353
30033081-EBP | 30033081-2026,AP,BYD,广州，Roll rubber, 260023,M,Equipment |  | 陈洁 | Phase 5 Production Delivery | 2026-03-03 |  | R | R | R |  |  | 无重大安全问题 设计自评后复合打分100% | 2026-02-12 | 2026-03-18 | 2026-04-22 | 260023
30034168-EBP | 30034168-2026,AP,SVW,A-SUV-mirror,assembly,260008,15T,Equipment |  | 周理文 | Phase 2 Concept Definition |  |  | Y | G | G |  |  |  | 2026-05-18 | 2026-06-18 | 2026-07-18 | 260008
30034171-EBP | 30034171-2026,AP,Jianghuai,JHC-sun visor,assy, 260074, NT,Equipment |  | 陈志斌 | Phase 2 Concept Definition |  |  | Y | G | G |  |  |  | 2026-05-18 | 2026-06-18 | 2026-07-18 | 260074
30034480-EBP | 30034480-2028,AP,Toyota,780B,Spraying,260086,T,Equipment |  | 陈子翌 | Phase0 |  |  | G | G | G |  |  |  | 2026-05-24 | 2026-06-24 | 2026-07-24 | 260086
30034479-EBP | 30034479-2027,AP,Toyota,780B,Spraying,260085,M,Equipment |  | 陈洁 | Phase0 |  |  | G | G | G |  |  |  | 2026-05-24 | 2026-06-24 | 2026-07-24 | 260085
30034478-EBP | 30034478-2026,AP,Toyota,780B-DP, flaming,260080,T,Equipment |  | 张帅 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-05-24 | 2026-06-24 | 2026-07-24 | 260080
30034477-EBP | 30034477-2025,AP,Toyota,780B-DP,Flaming, 260079,M,Equipment |  | 黄琳健 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-05-24 | 2026-06-24 | 2026-07-24 | 260079
30034166-EBP | 30034166-2026,AP,SAIC-GM,C1UL-2,CNSL,Lamination,260073,T,Equipment |  | 樊爱强 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-05-28 | 2026-06-28 | 2026-07-28 | 260073
30034615-EBP | 30034615-2026,AP,BYD,MR&ST-IP, Glue,260091, M,Equipment |  | 陈洁 | Phase 2 Concept Definition |  |  | G | G | G |  |  |  | 2026-05-30 | 2026-06-30 | 2026-07-30 | 260091
30034473-EBP | 30034473-2026,AP,SERES Motors,F2N-light,260081,M,Equipment |  | 郝秀霞 | Phase 3 Design Feasibility |  |  | R | R | G |  |  |  | 2026-04-24 | 2026-04-30 | 2026-06-30 | 260081
30035096-EBP | 30035096-2026,AP,smartmi,F2N-light,welding260130,M,Equipment |  |  | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-07-03 | 2026-08-03 | 2026-09-02 | 260130
30035089-EBP | 30035089-2026,AP,SAIC-GM,E2LB-2-IP, Automation, 260129, M,Equipment |  | 王晓宇 | Phase 1 Quotation |  |  | Y | G | G |  |  |  | 2026-05-16 | 2026-05-23 | 2026-06-13 | 260129
30034880-EBP | 30034880-2026,AP,GAC,GAC-IP,Laser,30032786,M,Equipment |  | 王万芳 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-08-04 | 2026-10-14 | 2026-10-30
30034747-EBP | 30034747-2026,AP,Huawei Anhui,X90-DP,260116,Glue spray,M,Equipment |  | 程德宝 | Phase 1 Quotation |  |  | Y | G | G |  |  |  | 2026-05-16 | 2026-05-23 | 2026-07-31 | 260116
30034746-EBP | 30034746-2026,AP,Huawei Anhui,X90-DP,260115,glue spray,M,Equipment |  | 程德宝 | Phase 2 Concept Definition |  |  | G | G | G |  |  |  | 2026-05-23 | 2026-06-06 | 2026-07-18 | 260115
30034624-EBP | 30034624-2026,AP,BYD,Lamination,260102,M,Equipment |  | 黄琳健 | Phase 2 Concept Definition |  |  | Y | G | G |  |  |  | 2026-05-16 | 2026-05-30 | 2026-07-31 | 260102
30034623-EBP | 30034623-2026,AP,BYD,Glue,260103,M,Equipment |  | 陈洁 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-05-22 | 2026-05-30 | 2026-06-20 | 260103
30034622-EBP | 30034622-2026,AP,BYD,Glue,260101,M,Equipment |  | 陈洁 | Phase 2 Concept Definition |  |  | G | G | G |  |  |  | 2026-06-27 | 2026-07-04 | 2026-07-11 | 260101
30033409-EBP | 30033409-2026,AP,Huawei Anhui,F05/F03 CNSL,Assembly,260037,M,Equipment |  |  | Phase 2 Concept Definition |  |  | Y | G | G |  |  |  | 2026-05-18 | 2026-06-18 | 2026-07-18 | 260037
30033407-EBP | 30033407-2026,AP,Huawei Anhui,F05/F03 CNSL,Assembly,260036,M,Equipment |  |  | Phase 2 Concept Definition |  |  | R | G | G |  |  |  | 2026-04-30 | 2026-05-31 | 2026-06-30 | 260036
30033405-EBP | 30033405-2026,AP,Huawei Anhui,F05 IP,Assembly,260038,M,Equipment |  |  | Phase 2 Concept Definition |  |  | R | G | G |  |  |  | 2026-04-30 | 2026-05-31 | 2026-06-30 | 260038
30033376-EBP | 30033376-2026,AP,Huawei Anhui,F05&F03,Assembly,260031,T,Equipment |  |  | Phase 2 Concept Definition |  |  | R | G | G |  |  |  | 2026-04-30 | 2026-05-21 | 2026-06-30 | 260031
30033375-EBP | 30033375-2026,AP,Huawei Anhui,F05&F03,Assembly,260032，T,Equipment |  |  | Phase 2 Concept Definition |  |  | R | Y | G |  |  |  | 2026-04-30 | 2026-05-19 | 2026-06-30 | 260032
30033373-EBP | 30033373-2026,AP,Huawei Anhui,F03F05,Assembly,260030,T,Equipment |  |  | Phase 2 Concept Definition |  |  | R | Y | G |  |  |  | 2026-04-30 | 2026-05-19 | 2026-06-30 | 260030
30035236-EBP | 30035236-2026,NA,Ford,P703-Airbag, assembly, 260142,1T,Equipment |  | 黄定辉 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-07-10 | 2026-08-10 | 2026-09-09 | 260142
30035209-EBP | 30035209-2026,AP,Jianghuai,C673-DP,Foam sticking,T,Equipment |  | 陈志斌 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-06-13 | 2026-06-30 | 2026-08-15
30035208-EBP | 30035208-2026,AP,Jianghuai,C673-DP,Foam Sticking,260140,M,Equipment |  | 陈志斌 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-05-31 | 2026-06-13 | 2026-07-18 | 260140
30035205-EBP | 30035205-2027,AP,SERES Motors,E68-DP,lamination,260138,2M,Equipment |  | 黄琳健 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-06-30 | 2026-07-30 | 2026-08-28 | 260138
30035188-EBP | 30035188-2026,AP,smartmi,KUNLUN-light,welding.260135.M,Equipment |  |  | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-07-04 | 2026-08-04 | 2026-09-03 | 260135
30034579-EBP | 30034579-2026,AP,BYD,Glue,260095,M,Equipment |  | 陈洁 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-07-06 | 2026-08-06 | 2026-09-05 | 260095
30034578-EBP | 30034578-2026,AP,BYD,Glue,260093,M,Equipment |  | 陈洁 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-07-04 | 2026-08-04 | 2026-09-03 | 260093
30034577-EBP | 30034577-2026,AP,BYD,EHX,Glue,260088,M,Equipment |  | 陈洁 | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-07-04 | 2026-08-04 | 2026-09-03 | 260088
30017341-EBP | 30017341-2024,AP,BYD,SA5-IP,Lamination,220281,M,Equipment | 尚兵 |  | Phase 1 Quotation |  |  | G | G | G |  |  |  | 2026-07-04 | 2026-08-04 | 2026-09-03 | 220281