## Sheet1
Project ID | Project Name | EBP Leader | Product Engineer | Project State | PKR_S | PKR | P2 | P3 | P4 | 备注 | SSO_S | SSO_issue | Phase 2 Gate Exit-DVR | Phase 3 Gate Exit-FPR | Phase 4 Gate Exit-CPA | 工作令号
30030292-EBP | 30030292-2027,AP,Mercedes-Benz,EU V530-IP,welding,250267,M,Equipment | 樊皆杰 | 郝秀霞 | Phase 4 Manufacturing Development | 2025-09-05 |  | R | R | Y | 车间 |  | 无重大安全问题 发运前安全状态分：81.68% | 2025-09-05 | 2025-09-28 | 2026-05-15 | 250267
30030290-EBP | 30030290-2027,AP,Mercedes-Benz,EU V530-IP, welding, 250266, T,Equipment | 樊皆杰 | 闵宏恩 | Phase 4 Manufacturing Development | 2025-09-18 |  | R | R | Y |  |  | 无重大安全问题 设计自评后复合打分100% | 2025-09-20 | 2025-11-20 | 2026-05-15 | 250266
30030289-EBP | 30030289-2027,AP,Mercedes-Benz,EU V530-IP, welding, 250265, T,Equipment | 樊皆杰 | 高一恒 | Phase 4 Manufacturing Development | 2025-09-25 |  | R | R | Y |  |  | phase2：缺少电气资料：唐兆丰 phase3：缺少电气资料：唐兆丰 | 2025-09-20 | 2025-10-18 | 2026-05-15 | 250265
30033578-EBP | 30033578-2026,AP,Tes,TBD_Click Rim, Lami, 260050, T,Equipment |  | 周华盛 | Phase 2 Concept Definition |  |  | R | G | G |  |  |  | 2026-05-12 | 2026-06-12 | 2026-08-31 | 260050
30035089-EBP | 30035089-2026,AP,SAIC-GM,E2LB-2-IP, Automation, 260129, M,Equipment |  | 王晓宇 | Phase 1 Quotation |  |  | Y | G | G |  |  |  | 2026-05-16 | 2026-05-23 | 2026-06-13 | 260129
30034747-EBP | 30034747-2026,AP,Huawei Anhui,X90-DP,260116,Glue spray,M,Equipment |  | 程德宝 | Phase 1 Quotation |  |  | Y | G | G |  |  |  | 2026-05-16 | 2026-05-23 | 2026-07-31 | 260116
30034624-EBP | 30034624-2026,AP,BYD,Lamination,260102,M,Equipment |  | 黄琳健 | Phase 2 Concept Definition |  |  | Y | G | G |  |  |  | 2026-05-16 | 2026-05-30 | 2026-07-31 | 260102